## INFORMAL PROJECTS
Project Priority List | [8 empty] | 2020-07-14 | [8 empty] | INFORMAL Projects
Unit | Campus Priority | Control Code | Project Status Block | Project Type | Department Code | Sub Department Name | Bldg Code | Building Name | Project Request Name | Project Description | Date Created | Project Account Manager | Project Customer | Financial Account Manager | Scope & Budget Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed | Estimated Design Complete | Notes
AA | 6 | AA-1414 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD BIOLOGY CAMERA REPLACEMENT | Woodward Biology Camera Replacement | 2017-05-16 13:26 | HUNTER, KATHY (kdwhaley) |  | HUNTER, KATHY (kdwhaley) | CAUDLE, AMANDA (afelock) | 18-0010 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Project on hold per Academic Affairs.
AA | 1 | AA-1696 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 233 CAGIS COMPUTER CLUSTER RELOCATION | McEniry-CAGIS Computer Cluster Relocation | 2020-03-12 10:36 | SCHAUBLE, DONIA (dcooke) | JONES, PATRICK (pajones) | MCMANNEN, TONYA (tmcmanne) | SPATARO, EVAMARIE (espataro) | 20-0194 | BOAL, JOHN (jboal1) | 55000 | 55000 | 0 | 2020-08-31 | (6/30/2020) Working with John Boal to integrate construction schedule
AA | 6 | AA-1440 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0057 | Duke Centennial Hall | DUKE 349 RENOVATIONS | Convert faculty lounge to office spaceContact Kevin Scott Smith for details 7-8350 | 2017-09-07 12:39 | HUNTER, KATHY (kdwhaley) |  | HUNTER, KATHY (kdwhaley) | BOAL, JOHN (jboal1) | 18-0049 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 6-23-2020 : On hold.
AA | 1 | AA-1704 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0031 | Cafeteria Activities Building | CAB KITCHEN EQUIPMENT DEMO | CAB-Kitchen Equipment Demolition | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0207-I | BOAL, JOHN (jboal1) | 53382 | 53382 | 0 | 2020-07-10 | 6-23-2020; Just received contractor proposal. Will prepare and submit the scope and budget in the next several days.
AA | 6 | AA-1531 | Project On Hold Design Services | Informal Projects | 24400 | Research & Economic Dev. VC | 0080 | PORTAL | PORTAL 232 AND 242 ENHANCEMENTS | PORTAL 322: 1) add color, texture, or paneling to the walls 2) move the UNCC sign in the space to different location 3) upgrade the photos and picture frames in the roomPORTAL 242: 1) add wall covering to wall outside of 242 and hang pictures like th | 2018-05-22 10:42 | MATEEN, ALI (amateen) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | HILL, CAROLINE (cmhill2) | 19-0001 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Customer has requested that this project should be place on hold until further notice.
AA | 6 | AA-1540 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0037 | McMillan Greenhouse | GREENHOUSE FOR BIOLOGY FACULTY | Greenhouse for Biology Faculty | 2018-06-29 09:17 | HUNTER, KATHY (kdwhaley) | SCHAUBLE, DONIA (dcooke) | HUNTER, KATHY (kdwhaley) | PATEL, NAVINKUMAR (npatel24) | 19-0023 | PATEL, NAVINKUMAR (npatel24) | 228650 | 0 | 0 |  | (07.07.2020) Waiting on Donia for scope of work and to set up meeting with end user. ON HOLD
AA | 0 | AA-1721 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY RESERACH LABS ABATEMENT | Asbestos Abatement to be completed in conjunction with McEniry HVAC & IT Infrastructure Replacement Capital Project | 2020-07-08 08:04 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 21-0004-I | BOAL, JOHN (jboal1) | 0 | 0 | 0
AA | 6 | AA-1610 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 391 RENOVATION | We are looking at splitting the room in two similar to 388/393.It may not be an exact half split though.We want one side to be a small PhD classroom and the other side to be a student bullpen area similar to 388/393.Classroom half needs to seat 20 if | 2019-04-10 13:24 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | TWEED, DANA (dtweed1) | HILL, CAROLINE (cmhill2) | 19-0204 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1616 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 242 CONFERENCE ROOM | I need a cost estimate to convert Friday 242 into a conference room. Move 1 display to the end wall. Remove the remaining 5 displays (Belk College Technology Team will take the 5 that get removed). Patch and paint walls. Core drill to connect lapto | 2019-04-22 13:35 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | SANCHEZ, STEPHANIE (ssanch12) | HILL, CAROLINE (cmhill2) | 19-0211 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Project on hold per customer request and lack of funding.
AA | 0 | AA-1722 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY RESERACH LABS - DEMO & HVAC | Demolition and HVAC work to be completed in conjunction with McEniry HVAC & IT Infrastructure Replacement Capital Project | 2020-07-09 08:27 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 21-0007-I | BOAL, JOHN (jboal1) | 0 | 0 | 0
AA | 6 | AA-1628 | Project On Hold Design Services | Informal Projects | 22000 | Mech Engineering & Engineering Sci | 0075 | Motorsports Research | MOTORSPORT WIND/TUN.STRUCT. ANALYSIS & POWER SPLY. | Motorsports Research Room 124 - Can we please have someone come out and approve the location of putting a concrete isolation pad in. Isolation pad will be provided by a 3rd party, we just need load approval for the floor below. | 2019-07-03 15:33 | CANTOR, MARION (mjcantor) |  | TADLOCK, ERICA (ewalter5) | SPATARO, EVAMARIE (espataro) | 20-0023 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Waiting on customer to assemble windtunnel and finalize where the equipment will reside in lab. Once complete, electrical can be run.
AA | 6 | AA-1629 | Project On Hold Design Services | Informal Projects | 24400 | Research & Economic Dev. VC | 0080 | PORTAL | PORTAL INTERIOR GRAPHIC SIGNAGE | We want signage to raise the profile of the Office of Tech Transfer, SBTDC, Ventureprise, 49er Foundry, and the PORTAL Solutions Desk. Signage needs to large enough to be seen from across the lobby, attractive, and professional. All of these offices | 2019-07-15 14:23 | MATEEN, ALI (amateen) |  | KEENE, PATRICIA (pgkeene) | TERRY, STEPHEN (slterry) | 20-0032 | TERRY, STEPHEN (slterry) | 10800 | 0 | 0 |  | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1632 | Project On Hold Design Services | Informal Projects | 17200 | Biological Sciences | 0056 | Woodward Hall | WOODWARD 461 EMERGENCY CIRCUIT | Woodward Hall - 461 - Add emergency circuit to lab (461). Almost a mirror project to the recently completed 361 | 2019-08-08 14:59 | GRAY, DAVID (dlgray) |  | GRAY, DAVID (dlgray) | SPATARO, EVAMARIE (espataro) | 20-0044 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Scope and budget provided to customer. Waiting on customer decision. Likely to be cancelled.
AA | 1 | AA-1439 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0073 | The Dubois Center | CCB 1101 RENOVATIONS | Upfit the third of three classrooms to be used as active learning environments. Estimate is based on cost to renovate Cameron 180. However, significant demolition was required in Cameron 180 that won't be required at Center City. It has been suggeste | 2017-09-07 12:35 | HUNTER, KATHY (kdwhaley) |  | HUNTER, KATHY (kdwhaley) | CAUDLE, AMANDA (afelock) | 18-0048 | CAUDLE, AMANDA (afelock) | 215000 | 215000 | 175544.66 | 2019-05-22 | (7-14-20) Project approx. 85% complete - wrapping up a furniture purchase
AA | 1 | AA-1623 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1040 ACTIVE LEARNING CLASSROOM | Colvard Classroom Active Learning | 2019-06-07 13:22 | HUNTER, KATHY (kdwhaley) |  | HUNTER, KATHY (kdwhaley) | CAUDLE, AMANDA (afelock) | 20-0008 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Construction underway. Project to complete by end of August.
AA | 1 | AA-1635 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD VIVARIUM AUTOCLAVE REPLACEMENT | Replace current vivarium autoclave with larger-capacity, internal-boiler autoclave. | 2019-08-15 11:48 | SCHAUBLE, DONIA (dcooke) | WILLIAMS, CHANDRA (cwill297) | MCMANNEN, TONYA (tmcmanne) | SPATARO, EVAMARIE (espataro) | 20-0049 | CAUDLE, AMANDA (afelock) | 200000 | 209000 | 19949.3 | 2020-04-30 | (7-14-20) Engineer drawings under review. Anticipate completion by end of July.
AA | 6 | AA-1638 | Project On Hold Design Services | Informal Projects | 15175 | Center City Campus | 0073 | The Dubois Center | CCB 1106 EXPANSION | Explore the possibility of remodeling and expanding 1106 at Center City. Remove wooden side walls and wall between 1106 and the storage areas behind it to make the room larger. | 2019-08-19 13:41 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | CAUDLE, AMANDA (afelock) | 20-0051 | CAUDLE, AMANDA (afelock) | 13000 | 0 | 0 |  | (7-14-20) Routed scope and budget for design 12/4/19. Pending customer approval to proceed. Placed on hold 6-26-20.
AA | 1 | AA-1640 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1021 STE TEACHING LEARNING CONNECTION RENO | Renovate Colvard 1021, 1021A-E for use by TLC. Renovation will include new paint and carpet and ceramic heat reflecting film on window glazing. | 2019-08-26 14:23 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0055 | CAUDLE, AMANDA (afelock) | 25000 | 25000 | 0 | 2020-03-27 | (7-14-20) PO's issued 3-31-20. Construction started 6-12 and complete by 6-30.
AA | 1 | AA-1680 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1043A-1057D DIST. ED MOVE FROM 1017 STE. | Colvard - 1031A, 1032A, 1033B, 1033C,1044A, 1045A, 1046A, 1047A, 1048A, 1048B, 1049A, 1050A, 1057, 1057A, 1057B, 1057C, 1057D - Move Distance Educatioin from Colvard Suite 1017 to new location on Colvard 1000 level. Project will require painting and | 2020-01-14 11:00 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0131 | CAUDLE, AMANDA (afelock) | 37000 | 37000 | 0 | 2020-06-15 | (7-14-20) Reached out to customer 7-7-20 for meeting to discuss scope and next steps.
AA | 6 | AA-1645 | Project On Hold Design Services | Informal Projects | 22150 | EPIC | 1055 | Lot 6 | LOT 6 - EV CHARGING STATION | Lot 6 - EV Charging Station: Provide an estimate for design and construction cost to install an experimental EV charging location. | 2019-09-09 13:42 | BROWN, LORI (lmorri25) | GAFFORD, JAMES (jgafford) | MOOSE, ROBIN (rmoose2) | SPATARO, EVAMARIE (espataro) | 20-0059 | SPATARO, EVAMARIE (espataro) | 11000 | 0 | 0 |  | (7/7/2020) On hold.
AA | 6 | AA-1660 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 310 HYDROLOGY & BIOCHEMISTRY LAB | Renovation of space on the on the 3rd floor as a hydrology and biochemistry lab and renovation of a classroom space on the 2nd floor. | 2019-11-06 12:30 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0084 | BOAL, JOHN (jboal1) | 35439 | 37439 | 24653.05 | 2020-05-29 | 6-23-2020: Scope of work has been significantly reduced. Redesign fee was submitted 5-11. Under review. FY 21 funding from AA.
AA | 6 | AA-1661 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 316 LANDSCAPE ECOLOGY LAB | Renovation of McEniry 316 and 313 for use as landscape ecology lab. | 2019-11-06 12:31 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0085 | BOAL, JOHN (jboal1) | 35000 | 38000 | 24346.63 | 2020-05-30 | 6-23-2020: Scope of work has been significantly reduced. Redesign fee was submitted 5-11. Under review. FY 21 funding from AA.
AA | 6 | AA-1663 | Project On Hold Design Services | Informal Projects | 18050 | DPT Writing, Rhet, Digital Studies | 0042 | Cameron Hall | CAMERON WRITING PROGRAM 1ST FLOOR SIGNS | CAMERON WRITING PROGRAM 1ST & 2ND FLOOR SIGNS: Name changes needed to Department of Writing, Rhetoric and Digital Studies. Several signs throughout first and second floors need to reflect our new name. Please contact Denise Sabo 7-1902 | 2019-11-15 13:46 | SABO, DENISE (dsabo1) |  | MULLIN, JOAN (jmulli40) | TERRY, STEPHEN (slterry) | 20-0089 | TERRY, STEPHEN (slterry) | 2900 | 0 | 0 |  | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1668 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0058 | Grigg Hall | GRIGG 386 CLEAN ROOM MOVE FROM CAMERON | Grigg - 386A - Move portions of existing Cameron clean room to Grigg 386A . This will locate all campus clean room functions into Grigg.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:19 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0120 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Working with Wei Gao on scope for equipment moves Will engage designer once scope is detailed. Will follow up with Donia regarding design fee.
AA | 6 | AA-1669 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD 264, 275 KINESIOLOGY MOVE FROM CAMERON | Woodward - 264, 275, 276, 276AMove Kinesiology Research labs from Cameron 2nd floor to Woodward 2nd Floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:25 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0121 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (6/23/20) Project on temporary hold until customer is back on campus
AA | 6 | AA-1670 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0017 | Belk Gymnasium | BELK GYM 024 KINESIOLOGY LAB | Belk Gym - 024 - Move human physiology research lab from Cameron 2nd floor to Belk Gym Ground floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:28 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0122 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 6-23-2020. Customer has been asked to provide additional scope information but not yet supplied it.
AA | 6 | AA-1671 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1028 FADO MOVE FROM CAMERON | Colvard - 1028, 1028A, 1028B, 1028C, 1028D, 1028E, 1028F, 1028G, 1028H, 1028I - Relocate FADO from Cameron 2nd Floor to Colvard 1000 level.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:46 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0123 | WELLS, ALICIA (awells43) | 10000 | 10000 | 0 | 2020-06-30 | (6/23/20) Renovation to start July/August. Move to take place when staff is back on campus.
AA | 6 | AA-1672 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0042 | Cameron Hall | CAMERON 174 MOSAIC MOVE FROM CAMERON | Cameron- Suite 174 - Relocate Mosaic from Cameron 2nd floor to Cameron 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:51 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0124 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (6/23/20) Customer meeting to schedule
AA | 6 | AA-1673 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS 146, 149 CNT. FOR GRAD.LIFE MOVE FROM CONE | Atkins - 146, 148A, 148B, Suite 149 - Move Center for ¦Graduate Life from Cone 2nd floor to Atkins 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0125 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1674 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0072 | EPIC Building | EPIC 1231 FURNITURE | EPIC - 1231 - Furniture Project - Exact scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble and Alicia Wells only. | 2020-01-14 10:01 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0126 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (6/23/20) Project on Hold
AA | 6 | AA-1676 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 217/218/220 SYST. ENGIN. MOVE FROM CAMERON | Smith - 205, 206, 211, 212, 213, 214, 216, 308,311,314,317,318,319,320, 320A,325,348,349,351,352 - relocate Systems Engineering from Cameron 2nd floor to Smith and create graduate bull pins for Engineering Technology graduate students who currently o | 2020-01-14 10:44 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0128 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Waiting on design fee from McVeign & Mangum. Will follow up with them this week.
AA | 6 | AA-1677 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 2 & 3 FLOOR CORRIDOR REFRESH | Smith - 245D and 2nd/3rd floor corridors - Provide AV upgrade for conference room 245D for use by Engineering Technology. Replace existing VCT possibly Asbestos containing in 2nd and 3rd floor corridors with LVT to match recently renovated hallways o | 2020-01-14 10:50 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0129 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | NNP - part of Cameron moves
AA | 1 | AA-1694 | Construction | Informal Projects | 23700 | Prec Metrology & Intellignt Mfg Ctr | 0057 | Duke Centennial Hall | DUKE 138 350FG MOORE MACHINE RELOC | Duke Centennial Hall - Rooms 132 & 151The following is requested :1. CSA Certified2. 208 3 Phase 30 AMP Breaker /40 AMP Fuses3. (3) 208 1 PHASE 10 AMP Each4. High Pressure Air from BoosterThis is needed to prepare the lab for Moore 350FG machine | 2020-02-25 15:30 | CHASTAIN, JENNIFER (jchasta4) | DUTTERER, BRIAN (bsdutter) | CHASTAIN, JENNIFER (jchasta4) | SPATARO, EVAMARIE (espataro) | 20-0181 | CAUDLE, AMANDA (afelock) | 11000 | 5000 | 0 | 2020-07-13 | (7-14-20) Zone 2 work request issued. Work to complete by 7/21 for equipment arrival on 7/24.
AA | 1 | AA-1707 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0052 | College of Education | COED 002-009 ACTIVE LEARNING CLASSROOM | COED Building - Rooms 002, 003, 005, 007, 009 - This project is meant to combine rooms 002, 005, and 007 into a large active learning classroom for 128 students. Room 009 would be converted into a graduate bull pin and room 003 would become a semina | 2020-04-09 11:12 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0219-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Reviewed scope with Donia Schauble on April 3. Mostly a furniture and technology purchase with very little construction. Work to complete by August 31.
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:10 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 |  | (6/30/20) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
AA | 6 | AA-1685 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS 330 NURSING SIMULATION LAB | CHHS - 330, 330A - Convert existing Classroom in School of Nursing Simulation Lab.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 11:12 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0134 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Waiting on Donia for equipment and project scope. ON HOLD
AA | 1 | AA-1683 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1017-1018 ACTIVE LEARNING CLASSROOM | Colvard - Suite 1017 and 1018A - Create new Active Learning Classroom.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:07 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 20-0132 | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 |  | Depedent on two other Colvard projects, no action until those projects move forward and have a clear schedule and plan.
AA | 6 | AA-1690 | Project On Hold Design Services | Informal Projects | 24200 | OneIT-CIO | 0001 | Kennedy | KENNEDY 320 RECONFIGURATION | We would like to discuss options for how Kennedy 320 can adjust for growth, specifically using 2 - 4 areas of existing space. Sandra Soriano (78987) is the contact for this request. | 2020-02-07 14:44 | VITALLO, JUDY (jvitallo) |  | VITALLO, JUDY (jvitallo) | HILL, CAROLINE (cmhill2) | 20-0170 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Scheduled to regroup on this project once campus has opened back up.
AA | 6 | AA-1692 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | BAND TOWER FOOTING DESIGN | Band Tower Footing Design - The marching band will be installing a pre-fabricated 24' tall steel tower at the practice field. The tower will need to have a footing designed by an NC licensed engineer. Getting a budget for this project is very urgent | 2020-02-12 10:38 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 20-0174 | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 |  | Restarting project, considering a temporary option + storage instead of the permanent tower. Arranging meeting with band group.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | 18000 | English | 0045 | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 2020-02-20 10:55 | WILLIAMS, ANGELA (anwillia) |  | WILLIAMS, ANGELA (anwillia) | SISCO, ASHLEY (asisco1) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (6/30/20) Per email from customer this project will be on hold.
AA | 0 | AA-1710 | Scope & Budget Requested | Informal Projects | 25000 | Library | 0041 | Storrs | STORRS 200 ARCHITECTURE LIBARY SHELVING | Secure a certified library mover to replace the existing vista base shelving in the architecture library at Storrs with welded frame shelving from the main library in order to create additional shelf capacity. | 2020-04-27 07:31 | REYNOLDS, MARK (mdreynol) | REYNOLDS, MARK (mdreynol) | BARTON, JESSICA (jbarto18) | FRERE, ELIZABETH (efrere) | 20-0230-I | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 |  | Gathering information, arranging meeting with users.
AA | 0 | AA-1711 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 1ST FL STUDIO KNEE WALL REMOVAL | SoA would like to remove the knee wall in the 1st year studio area on the 1st floor. Once the wall is removed VCT in the area will need to be patched. | 2020-04-27 07:32 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 20-0234-I | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 |  | Gathering information, arranging meeting with users.
AA | 0 | AA-1719 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | STORRS, ROBINSON & ROWE ARTS QUAD | Quad between Storrs, Robinson, and Rowe - The arts quad project is intended to provide canopied space for outdoor art and architecture teaching. Tented structures will cover areas of the quad and the recessed yard in front of Storrs. Amenities will | 2020-07-01 13:46 | SCHAUBLE, DONIA (dcooke) | MULLER, BROOK (bmuller7) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 21-0001-I | FRERE, ELIZABETH (efrere) | 0 | 0 | 0
AA | 6 | AA-1698 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0080 | PORTAL | PORTAL 129 UPGRADES | Portal - 129 - Upgrades to Active Learning Classroom | 2020-03-16 08:25 | SCHAUBLE, DONIA (dcooke) | TANKERSLEY, RICHARD (rtankers) | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0199-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 0 | AA-1720 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | LIBRARY LEASE SPACE | Work related to kick off library off campus space lease. | 2020-07-08 07:58 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 21-0002-I | FRERE, ELIZABETH (efrere) | 0 | 0 | 0
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 2020-03-16 08:40 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (6/30/20) Per email from Donia on 5/27 this project will be placed on hold. Will revisit in 6 months.
AA | 6 | AA-1702 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS VIRTUAL CADAVER LAB | CHHS - Virtual Cadaver Lab | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0205-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Waiting on information from Donia regarding location, and equipment. ON HOLD
AA | 1 | AA-1641 | Construction | Informal Projects | 15215 | Performing Arts Services (PAS) | 0051 | Robinson Hall | ROBINSON 220 FACULTY OFFICE | Need to create a new faculty office from the alcove part of Robinson 220 that is adjacent to 221 and create a separate entrance into the hallway. This project should be similar to the one recently done for Robinson 124. | 2019-08-27 17:32 | LUEKE, BEVERLY (bblueke) | LUEKE, BEVERLY (bblueke) | RUCKER, BETH (aefird) | HILL, CAROLINE (cmhill2) | 20-0075 | HILL, CAROLINE (cmhill2) | 8200 | 7050 | 7050 | 2020-06-30 | 6/29/2020 - Regrouping with FO employees to try and push this project forward.
AA | 1 | AA-1697 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0051 | Robinson Hall | ROBINSON BELK THEATER ORCHESTRA PIT LIFT | Replacement of Orchestra Lift | 2020-03-16 08:25 | SCHAUBLE, DONIA (dcooke) | LUEKE, BEVERLY (bblueke) | MCMANNEN, TONYA (tmcmanne) | LINGER, JOSHUA (jlinger2) | 20-0198-I | LINGER, JOSHUA (jlinger2) | 268293.64 | 268293.64 | 0 | 2020-08-28 | 07/07/2020 Planning to have the materials onsite no later than September 1st. The lift should be up and running in about two weeks after we get the components.
AA | 1 | AA-1705 | Req Scope & Budget Review | Informal Projects | 15100 | Academic Affairs VC | 0075 | Motorsports Research | MOTORSPORTS VIBRATION PAD | Motorsports research needs to have their existing vibration pad permanently floor mounted. Adam Stall has a specific location in mind and needs to find out if the pad can be mounted in that location. Costs for the work must be identified and approv | 2020-03-30 17:31 | SCHAUBLE, DONIA (dcooke) | STALL, ADAM (astall) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0214-I | PATEL, NAVINKUMAR (npatel24) | 4000 | 0 | 0 |  | (07.07.2020) Received structural engineering and locate services proposal 07.07.2020. Will complete scope and budget and route back to PAM and FAM no later than 07.08.2020.
AA | 6 | AA-1706 | Project On Hold Design Services | Informal Projects | 15300 | College of Liberal Arts & Sciences | 0045 | Fretwell | FRETWELL 3RD FLOOR ATRIUM NAMING | Fretwell 3rd Floor Atrium Naming. Dr. Robert & Mrs. Tiwana Anderson Atrium Signage and Portrait development and installation | 2020-03-31 17:42 | FRIZZELL, MARY ELLEN (mfrizzel) | LEKOSKI-EURICH, JUDY (jlekoski) | STAFFORD, ELEANOR (eastaffo) | TERRY, STEPHEN (slterry) | 20-0217-I | TERRY, STEPHEN (slterry) | 5400 | 0 | 0 |  | 06-03-20. No change. Budget review. Customer said to hold.
AA | 0 | AA-1714 | Construction | Informal Projects | 28350 | AISLE | 0038 | Burson | BURSON, CAMERON, COED, CHHS SIMULCAST CLASSROOMS | Burson 115, Cameron 101, COED 065, CHHS 281 we will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0252-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 2020-06-30 | (07.07.2020) Waiting on purchasing for approval. Project will be in construction by 07.09.2020.
AA | 0 | AA-1715 | Construction | Informal Projects | 28350 | AISLE | 0045 | Fretwell | FRET, FRIDAY, MCENIRY, DENNY SIMULCAST CLASSROOMS | Fretwll 128, Friday 137, McEniry 117 Denny220. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0253-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 2020-06-30 | (07.07.2020) Project has been approved by FAM and PAM will place project into construction on 07.10.2020.
AA | 0 | AA-1716 | Construction | Informal Projects | 28350 | AISLE | 0017 | Belk Gymnasium | BELK GYM, DUKE, EPIC SIMULCAST CLASSROOMS | Belk Gym 201, Duke 345, Epic 2222. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0254-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 2020-06-30 | (07.07.2020) Project has been approved by FAM and PAM will place project into construction on 07.09.2020.
AA | 0 | AA-1717 | Construction | Informal Projects | 28350 | AISLE | 0019 | Rowe | ROWE, SMITH, STORRS, WOODWARD SIMULCAST CLASSROOMS | Rowe 161, Smith 202, Storrs 290, Woodward 155. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:13 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0255-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 2020-06-30 | (07.07.2020) Project has been approved by FAM and PAM will place project into construction on 07.08.2020.
AA | 0 | AA-1718 | Scope & Budget Requested | Informal Projects | 24400 | Research & Economic Dev. VC | 0058 | Grigg Hall | GRIGG 330 SAFETY SHOWER | Grigg Hall - 330 - We would like a quote to purchase and install a lab safety shower. Is the current plumbing sufficient and can it be tied into the tempered water line? Need an idea of the timeline. | 2020-06-29 14:26 | MATEEN, ALI (amateen) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | PATEL, NAVINKUMAR (npatel24) | 20-0258-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Waiting on Facilities to provide a proposal of work. We should get this by 07.08.2020.
AA | 1 | AA-1446 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL FIRST FLOOR LOBBY RENOVATION | Plans for renovation of Fretwell first floor (open public space).Contact Shawn Long for details 7-0075 | 2017-09-07 15:06 | HUNTER, KATHY (kdwhaley) | LONG, SHAWN (sdlong) | HUNTER, KATHY (kdwhaley) | SISCO, ASHLEY (asisco1) | 18-0060D&C | SISCO, ASHLEY (asisco1) | 34000 | 34000 | 30900 | 2018-08-13 | (6/30/20) Meeting with Jay, Donia, Kathryn, and CLAS 7/2.
AA | 1 | AA-1634 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0048 | SISCO, ASHLEY (asisco1) | 27589 | 80000 | 57128.12 | 2019-11-13 | (6/30/20) Furniture to install around August 24th.
AA | 0 | AA-1636 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0050 | SISCO, ASHLEY (asisco1) | 17171 | 17171 | 0 | 2020-08-31 | (6/30/20) PO's issued. Project to be complete by start of fall classes.
AA | 1 | AA-1703 | Req Design Estimate Review | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 230, 222B, 274, 276 RENOVATIONS | Storrs - Rooms 230, 222B, and 274/276 - Additional work and furniture needed to accommodate space changes that will take place as part of the Capital ITS Infrastructure Replacement work in the Storrs building. | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0206-I | SISCO, ASHLEY (asisco1) | 77000 | 77000 | 0 | 2020-09-07 | (6/30/20) Met on site with customer 6/30 to look at all the spaces. This project will piggy back off the capital project.
AA | 0 | AA-1713 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 4077-4085 FACULTY START UP | Reconfigure former spaces 4077, 4078, 4080, 4081, 4084, and 4085 into 3 spaces needed for Psychology research. This is part of a new faculty start up. | 2020-06-13 13:11 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0249-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (6/30/20) Project kick off meeting with Donia and Dr. Heggestad. 6/22/20
AA | 0 | AA-1723 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0057 | Duke Centennial Hall | DUKE 313 REFRESH | This project is intended to provide a refresh of the Dean's office in COE. Some wall repair is needed as well as wallpaper removal, paint, new carpet in installation of a metal stud mounted glass marker board. | 2020-07-09 08:27 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 21-0008-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0
AA | 1 | AA-1700 | Scope & Budget Requested | Informal Projects | 22150 | EPIC | 0072 | EPIC Building | EPIC HIGHBAY WINCH POWER CONNECTION | Please install three 460V 3phase power connections in the EPIC highbay lab. | 2020-03-16 08:40 | MOOSE, ROBIN (rmoose2) | PARK, YOUNGJIN (ypark17) | MOOSE, ROBIN (rmoose2) | SPATARO, EVAMARIE (espataro) | 20-0203-I | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Showed rough estimate to customer, customer needs to research funding options
AA | 1 | AA-1556 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0537 | Sycamore | SYCAMORE FF&E | Sycamore FFEThe units that are moving are:Urban Institute_Contact: Jeff MichaelMetropolitan studies_ Contact: Curt WaltonInstitutional research_Contct: Steve Coppola | 2018-10-05 15:11 | HUNTER, KATHY (kdwhaley) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 19-0067F | WELLS, ALICIA (awells43) | 315000 | 419880 | 398114.67 | 2019-02-19 | (6/23/20) Move complete. Finalize punch list items
AA | 1 | AA-1686 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY FF&E | McEniry - Furniture Project - Full scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 11:23 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0135 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (6/23/20) furniture layouts & pricing to Donia by 7/1
AA | 1 | BA-1923 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0097 | Science Building | SCIENCE FF&E | SCIENCE FF&E: Furniture for the new Science building & Data Center. Capital funded project. Project Dollar Maximum; $1,500,000. Assign to Alicia Wells. | 2020-02-19 15:35 | FAKE, WILLIAM (wmfake) |  | CEALLAIGH, SHERRYL (sceallai) | WELLS, ALICIA (awells43) | 20-0176 | WELLS, ALICIA (awells43) | 1500000 | 1500000 | 0 | 2021-08-31 | (6/23/20) RUP Data Center furniture ordered and will install after BO
BA | 6 | BA-1544 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS WIDE BUILDING EVACUATION MAPS | Building evacuation interior floor plan maps need to be installed in all buildings. The Office of Environmental Health and Safety would like to request an official scope and budget to install these maps. | 2017-03-07 16:43 | GRIFFIN, DARIUS (dgriffin) |  | GRIFFIN, DARIUS (dgriffin) | TERRY, STEPHEN (slterry) | 17-0195 | TERRY, STEPHEN (slterry) | 0 | 0 | 0 |  | (06-03-20) - Still on hold for funding. Scope was provided to EHS for funding review.
BA | 6 | BA-1586 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT: Congestion Task Force assignment for design only: Central Funds - Project Dollar Maximum: $13,000. | 2017-05-17 07:56 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | KELLY, SHAWN (skelly64) | 17-0225 | KELLY, SHAWN (skelly64) | 13000 | 13000 | 11731.7 | 2017-05-29 | On Hold till Funding Approved
BA | 6 | BA-1631 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0068 | Bioinformatics | FPFM, BIOINFORMATICS 124 CODE ROOM USE SEPARATIONS | FPFM - BIOINFORMATICS 124 CODE REQUIRED ROOM USE SEPARATIONS: Mechanical, storage and wood shop uses need separation by 2-hour fire walls. Construction costs unknown. Outside design is required at $30,000. | 2017-11-02 06:48 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | BOAL, JOHN (jboal1) | 18-0089 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 6-23-2020: Project not funded.
BA | 6 | BA-1676 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, CAMPUS ADA PATHWAYS SURVEY DATA REVIEW | FPFM, REVIEW RECENTLY COMPILED CAMPUS ADA PATHWAYS SURVEY DATA TO MAKE RECOMMENDATIONS FOR CHANGES TO CAMPUS MAP: Point of contact: Katie Montie with Disability Services (DS). Facilities Information Systems (FIS) to provide technical assistance. | 2018-03-07 06:37 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 18-0178 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | Following Up with Customer To Closeout
BA | 6 | BA-1680 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS SERVICE VEHICLE SIGNAGE | Please provide a proposed scope and budget for the project detailed below. Once the scope and budget is received, our office will be able to determine if the project can be completed this fiscal year or in the next.Approximately 15 marker post signs | 2018-04-02 16:44 | GRIFFIN, DARIUS (dgriffin) | ALSTON, TAMEKA (talsto16) | BARNETT, DENISE (dbarne33) | TERRY, STEPHEN (slterry) | 18-0198 | TERRY, STEPHEN (slterry) | 18500 | 0 | 0 |  | (06-03-20) - Still on hold for funding. Scope and preliminary designs were provided to EHS for review.
BA | 6 | BA-1696 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1007 | Union Deck | UNION DECK STORAGE ROOM | UNION DECK Storage Room, provide large storage room on level 1 underneath of the up ramp where area is fenced off. This modification was rejected in the Expansion project due to schedule but we would like to review requirements and price out impleme | 2018-05-07 09:37 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | CAUDLE, AMANDA (afelock) | 18-0232 | CAUDLE, AMANDA (afelock) | 225000 | 0 | 0 |  | (7-14-20) Project on Hold
BA | 6 | BA-1762 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1056 | Lot 7 | LOT 7 & 7A RECONFIGURATION | LOT 7 & 7A Reconfiguration, redesign Lots 7 and 7A to optimize usage and traffic flow (Design only at this point in time). | 2019-01-07 10:46 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 19-0106 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | On Hold Pending Cone Deck Decisions
BA | 6 | BA-1871 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING: Need Scope & Budget to allow further review by Jon Varnell to allow assessment of funding options. Please assign to Steve Terry. | 2019-11-18 10:44 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | TERRY, STEPHEN (slterry) | 20-0088 | TERRY, STEPHEN (slterry) | 30000 | 30000 | 0 | 2020-06-12 | 06/03/20. No change. Budget review. Customer said to hold.
BA | 2 | BA-1910 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 4012 | Amay James Pre-K Center | NINER UNIVERSITY ELEMENTARY DESIGN & CONSTRUCTION | NINER UNIVERSITY ELEMENTARY D&C: Amay James Pre-K Center: Select Architect, Mecklenburg County permitting, Construct front office, add ADA All Gender family restroom, electrical, data, flooring, paint, and ADA door hardware. $290,000. Amanda Caudle. | 2020-01-24 08:11 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 20-0153 | CAUDLE, AMANDA (afelock) | 290000 | 290000 | 24508.28 | 2020-01-27 | (7-14-20) Permit in hand 6/23/20. Work to complete by early August.
BA | 2 | BA-1911 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 4012 | Amay James Pre-K Center | NINER UNIVERSITY ELEMENTARY FF&E | NINER UNIVERSITY ELEMENTARY FF&E: Provide the following: (1) Furniture for eleven classrooms, reception area, media center, and cafeteria. (2) Classroom technology. (3) Signage. Project Dollar Maximum: $590,000. Assign to Amanda Caudle. | 2020-01-24 08:14 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 20-0154 | CAUDLE, AMANDA (afelock) | 590000 | 590000 | 131599.87 | 2020-01-27 | (7-14-20) Furniture PO issued April 27. Installation to complete by 7-31-20.
BA | 2 | BA-1919 | Scope & Budget Requested | Informal Projects | 10500 | Auxiliary Operations | 0082 | South Village Crossing | SVC TERRACE FURNITURE | SVC Terrace Furniture, propose, review and provide exterior furniture and accessories on the upper floor terrace area. Replace and or relocate existing furniture as supports the overall plan fo rthe terrace. | 2020-02-10 11:20 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0167 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Creating RFP for designers.
BA | 1 | BA-1922 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0073 | The Dubois Center | CCB FIRST FLOOR SINGLE USE RESTROOM | CCB FIRST FLOOR SINGLE USE RESTROOM: Uses some space within Food Service area. Reconfigure Food Service area as part of design. Design only at this point for $30,000. Total Project Dollar Maximum: $175,000. Assign to Amanda Caudle. | 2020-02-13 15:10 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | CAUDLE, AMANDA (afelock) | 20-0175 | CAUDLE, AMANDA (afelock) | 30000 | 118552.62 | 111347.62 | 2020-02-14 | (7-14-20) Year end funding complete. Project is under construction with completion by mid-August.
BA | 2 | BA-1945 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | DINING SEAT CUSHIONS | SEAT CUSHIONS, various locations, need to provide seat cushions for all hard wood seats. Includes Prospector, Student Union, SVC. Project will have to be bid given the number of seats. | 2020-04-10 12:56 | AVERITT, DREW (daveritt) | HOLMES, ROBERT (rholme16) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0222-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Working on request for pricing for material management bidding. Drew and I captured all chair information necessary for bidders. Chair samples delivered 6-29 for customer feedback on foam selection and construction.
BA | 0 | BA-1968 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0082 | South Village Crossing | SVC SUN SAILS | SVC Sun Sails, provide sun sails over portions of the terrace area. | 2020-07-08 07:58 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0003-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Working with Alpha Canvas to develop scope.
BA | 0 | BA-1969 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR COVID DINING MODIFICATIONS | PROSPECTOR Covid Modifications, modify Prospector as follows: 1. All wall in Servery 200, patch and paint wall in 200 common with 200C. Remove and store door (at CAB) between 200/202. 2 Remove portion of 4th cashier stand (end wall where cash regi | 2020-07-13 13:57 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0010-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0
BA | 6 | BA-1930 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0001 | Kennedy | KENNEDY CONTEMPLATIVE SPACE RENOVATION | KENNEDY CONTEMPLATIVE SPACE RENOVATION, DESIGN: Chancellor 2020 Central Funds: $50,000. Design Only. Project Dollar Maximum: $30,800.00. | 2020-03-04 07:20 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0184 | FRERE, ELIZABETH (efrere) | 30800 | 30800 | 30800 | 2020-04-15 | (05-08-2020) Watson Tate Savory total design contract reduced to $29,920. Partial invoice for $23,222.10 dated 04-23-2020 was approved for payment on 04-27-2020.
BA | 0 | BA-1970 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0069 | Popp Martin Student Union | STUDENT UNION COVID DINING MODIFICATIONS | SU Covid Modifications 1. at Bojangles, remove low wall and counter across from Bojangles BOH door and cashiers. Remove counter only at low wally near Bojangles pick up area. Need to determine how to treat top of wall - looks like we can cut stone | 2020-07-13 13:57 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0011-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0
BA | 0 | BA-1971 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0069 | Popp Martin Student Union | STUDENT UNION 137-138 STORAGE ROOM MODIFICATIONS | SU Storage Room Modifications, modify 137 and 138 to remove demizing wall. Relocate some metal shelving. Need large item storage and pallet drop area. Provide rolling plastic shelving typical of our dry storage areas to provide more storage within | 2020-07-13 13:57 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0012-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0
BA | 2 | C-0041 | Construction | Informal Projects | 10250 | Legal Affairs | 0048 | Cato Hall | CATO 1ST FL TITLE IX & INTERNAL AUDIT | Title IX & Internal Audit Cato Hall first floor renovations. | 2020-03-30 17:31 | JOHNSON, MELANIE (mmjohns1) | HUMPHREY, JAMES (jhumph19) | SHUE, BRENDA (bshue3) | CAUDLE, AMANDA (afelock) | 20-0215-I | CAUDLE, AMANDA (afelock) | 210000 | 210000 | 30797.4 | 2020-05-18 | (7-14-20) Work in progress. Anticipate completion by the end of August.
BA | 6 | BA-1959 | Project On Hold Design Services | Informal Projects | 10500 | Auxiliary Operations | 1057 | Lot 8 | LOT 8 HOUSING VEHICLES SIGNAGE | Install signs for Housing vehicles in Lot 8 (I would call "Lot 8 signage) | 2020-05-13 11:05 | HOLMES, ROBERT (rholme16) | LAPE, DOUGLAS (dlape) | MULLMANN, JANETTA (jmullman) | TERRY, STEPHEN (slterry) | 20-0240-I | TERRY, STEPHEN (slterry) | 0 | 0 | 0 |  | 06-03-20 - Site meeting on hold.
BA | 2 | BA-1927 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR DOOR REPLACEMENT | PROSPECTOR Door Replacement, replace the (5) full glass door locations with standard doors. There are (3) exterior pairs of doors (tied into Open Options), (1) interior vestibule pair of doors and (1) interior pair of doors (needs to lock). Pending | 2020-02-27 11:42 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | LINGER, JOSHUA (jlinger2) | 20-0190 | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 |  | 0707/2020- waiting on proposal from vendor
BA | 1 | BA-1920 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0092 | Facilities Ops and Parking (FOPS) | MOVE FIS TO FOPS FACILITIES OPERATIONS | FPFM, MOVE FIS TO FOPS, FACILITIES OPERATIONS & PARKING SERVICES BUILDING: Moves Management: | 2020-02-11 05:24 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | CLARK, VALERIE (vclark9) | 20-0168 | SISCO, ASHLEY (asisco1) | 5000 | 80040.46 | 79724.1 | 2020-04-24 | (6/30/20) Project complete. Working on final invoicing
BA | 2 | BA-1894 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | 2020 CAMPUS PARKING MISC. SIGNS #1 | 2020 CAMPUS PARKING MISC. SIGNS #1, various signs as needed as done in years past. First 2 items are: 1) Replace damaged HC sign in Lot 7 with flex post. 2) Install 2 new spaces in Lot 16 for Geography and Earth Sciences vehicles. | 2020-01-23 08:54 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | TERRY, STEPHEN (slterry) | 20-0139 | TERRY, STEPHEN (slterry) | 7000 | 7000 | 2250 | 2020-03-06 | (06-03-20) - Current work Complete. Nancy to provide other sign needs to use remaining balance. Project to remain open.
BA | 0 | UA-0057 | Req Design Estimate Review | Informal Projects | 30600 | UA Business Operations | 0071 | UNC Charlotte Foundation | ALBERT-FREEMAN EPIC | Adjust signage for Building changes and directional signage for Albert- Freeman Epic Steve Terry is involved working with Beth Crigler and Meagan Jones | 2020-07-10 11:26 | WIDMAIER, CLEO (cswidmai) | WIDMAIER, CLEO (cswidmai) | WIDMAIER, CLEO (cswidmai) | TERRY, STEPHEN (slterry) | 21-0009-I | TERRY, STEPHEN (slterry) | 37757 | 37757 | 0 | 2020-09-18
BA | 1 | BA-1947 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0054 | Bissell House | BISSELL HOUSE 2020 RENOVATION | BISSELL HOUSE 2020 RENOVATION: Project Dollar Maximum: $300,000.00 using Chancellor's Central Funds (year-end one-time funds). Assign to Alicia Wells. | 2020-04-15 06:45 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0224-BA | WELLS, ALICIA (awells43) | 300000 | 225652.42 | 154209.95 | 2020-06-19 | (6/23/20) Project is split funded. Close out mid July
BA | 6 | UA-0039 | Project On Hold Design Services | Informal Projects | 30300 | Alumni Affairs | 0088 | Hauser Alumni Pavilion | HAUSER ALUMNI PAVILION SECURITY DOORS | Project to add garage door type security between the brick columns . Cleo - use 138062. Contact Scott Plunkett at 7-7792 | 2017-11-14 09:27 | PLUNKETT, SCOTT (ssplunke) |  | WIDMAIER, CLEO (cswidmai) | CAUDLE, AMANDA (afelock) | 18-0101 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Project to remain on hold per Scott Plunkett.
BA | 0 | BA-1956 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0054 | Bissell House | CHANCELLOR LOT EXTERIOR UPGRADES | CHANCELLOR LOT EXTERIOR UPGRADES: Project Dollar Maximum: $100,000.00 using Chancellor's Central Funds. Includes excavation design & construction, waterproofing, plants & bushes replanting, and soil compaction. Assign to Alicia Wells. | 2020-05-11 12:19 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0237-BA | WELLS, ALICIA (awells43) | 100000 | 300000 | 289054.34 | 2020-06-24 | (6/23/20) Split funding. Project to be completed by first week of July
IF | 0 | BA-1966 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0536 | Hickory | HICKORY INVERTER - EGRESS LIGHTING - 2 | HICKORY INVERTER - EGRESS LIGHTING - 2: Phase 2 of the Hickory Invertor for Egress Lighting. Scheduled to complete early FY-2021. Project Dollar Maximum: $7,000. Funding Source: 336487 (Design Fees). Assign to Amanda Caudle. | 2020-06-15 12:02 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | PAQUETTE, NOELLA (njpaquet) | FAKE, WILLIAM (wmfake) | 20-0250-I | CAUDLE, AMANDA (afelock) | 7000 | 7000 | 0 | 2020-06-15 | (7-14-20) Work in progress. Anticipate completion by end of July.
IF | 2 | BA-1929 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | MEMORIAL STRUCTURAL SCULPTURE DESIGN | MEMORIAL STRUCTURAL SCULPTURE DESIGN: Structural design for steel memorial sculpture with foundation in University Gardens to contain large stones with student etched memorials. Pro Bono (no cost) design by SKA Consulting Engineers. Fund: 336487. | 2020-03-02 09:05 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0182 | FAKE, WILLIAM (wmfake) | 1 | 1 | 0 | 2020-10-30 | (05-08-2020) - Design by SKA (Garrett Overcash) to be complete by June 15, 2020 ready for SCO submission. Construction to occur between early September and late November - Needs a project request entry by Student Affairs. SteelFab Inc. involved with pricing options.
IF | 6 | AA-1655 | Project On Hold Design Services | Informal Projects | 15175 | Center City Campus | 0073 | The Dubois Center | CCB OUTDOOR LIGHTING | Additional lighting needs to be added to the back garden area. Please assess the current lighting, make recommendations for additional and adequate lighting and provide an estimate of cost. | 2019-10-10 12:30 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | SPATARO, EVAMARIE (espataro) | 20-0079 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Customer has received estimates. Waiting on decision.
IF | 2 | BA-1090 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | CAMPUS WIDE PARKING DECK REPAIR SURVEY - DES | CAMPUSWIDE Parking Deck Repair Survey. Provide bids for report documenting observations and typical inspection checklists for all existing decks (through Deck J / South Village Deck). Original basis is the SKA report provided to Jeff Ross dated Jan | 2013-06-28 11:19 | AVERITT, DREW (daveritt) | LAPE, DOUGLAS (dlape) | AVERITT, DREW (daveritt) | KELLY, SHAWN (skelly64) | 14-0009D | KELLY, SHAWN (skelly64) | 109180 | 92150 | 90500 | 2019-01-25 | On Going 5 Year Parking Deck Study Currently in Year 2 of Study
IF | 2 | BA-1759 | Construction | Informal Projects | 10400 | Business Services AVC | 1007 | Union Deck | UNION DECK MODIFY GUARDRAIL | UNION DECK, Modify Guardrail, guardrail on north face of the original deck on the sloped/ramp driveway is below 42" and does not comply with code. Guardrails at flat/level portions are at 42" so OK. Provide metal and cable guardrail extension as pr | 2018-12-13 11:45 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | KELLY, SHAWN (skelly64) | 19-0099 | KELLY, SHAWN (skelly64) | 50000 | 63500 | 58878.6 | 2020-01-31 | 06/26/20: Projected Project Closeout Note: Currently Addressing Punch List Issues
IF | 2 | BA-1853 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | CAMPUS WIDE PARKING DECK REPAIRS PHASE 1 | CAMPUS WIDE PARKING DECK REPAIRS, provide recommended repairs for year 1 work as outlined by THP Limited, Inc. in various decks as outlined in previous reports and meetings. Please assign to Shawn Kelly. Thanks. | 2019-07-15 15:25 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | KELLY, SHAWN (skelly64) | 20-0033 | KELLY, SHAWN (skelly64) | 275000 | 275000 | 225585.16 | 2019-08-16 | 07/31/20: Construction Complete 08/07/20: Projected Project Closeout Note: Awaiting Special Order Brick to complete Year 1 Masonry Repairs.
IF | 2 | BA-1860 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR DUMPSTER BOLLARDS | PROSPECTOR, provide dumpster bollards. The 2 dumpsters (trash and recycling - 10CY) have a tendency to migrate out into the drive lanes until we reset them. Trucks are forced to have to maneuver around them to access the loading dock. We need to d | 2019-09-23 10:28 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0066 | KELLY, SHAWN (skelly64) | 9500 | 9500 | 0 | 2020-01-31 | 06/01/20: Construction Completed 06/26/20: Projected Project Closeout
IF | 2 | BA-1865 | Construction | Informal Projects | 10400 | Business Services AVC | 0029 | Housing and Residence Life | HOUSING & RESIDENCE LIFE LOADING DOCK LADDER | HRL, Loading Dock Ladder, add metal ladder at the catering loading dock between the two truck bays with roll over grab bars. This is required as drivers are jumping off dock rather than using nearby stairs. | 2019-10-28 12:02 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0091 | KELLY, SHAWN (skelly64) | 1500 | 1500 | 184.14 | 2020-02-28 | 06/01/20: Construction Completed 06/26/20: Projected Project Closeout
IF | 1 | BA-1938 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | CRI BUS PULL OFF DESIGN | CRI BUS PULL OFF DESIGN: Assign to Shawn Kelly. Project Dollar Maximum: $25,000. | 2020-03-16 15:35 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0210-I | KELLY, SHAWN (skelly64) | 25000 | 21305.55 | 20872.95 | 2020-06-12 | Project Financials 100% Complete & Ready for Closeout.
IF | 0 | BA-1950 | In Design | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, PPS & ITS DUCK BANK AT EVI | FPFM, PPS & ITS DUCK BANK AT EVI: Create duct bank connection on campus for AT&T, CenturyLink on John Kirk. Determine route on Martin Village Connector to terminate at existing MH 94 on Martin Village Road. Coordinate with EVI and Lot 5A Projects. | 2020-04-20 16:30 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 20-0228-I | KELLY, SHAWN (skelly64) | 300000 | 0 | 0 |  | 06/01/20: Awaiting clarification on funding and direction from ITS & Police on how to proceed and how project will be funded. To Be Determined: Project Future
IF | 0 | BA-1965 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0029 | Housing and Residence Life | HRL CATERING SCREEN WALL | HRL, Catering Screen Wall, provide fence or green wall in and around the Catering cart/van parking area as students are cutting through area with near misses and some students jumping off the loading dock presenting lots of safety issues. Please ass | 2020-06-10 07:56 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0247-I | KELLY, SHAWN (skelly64) | 0 | 0 | 0
IF | 0 | BA-1967 | Scope & Budget Requested | Informal Projects | 13930 | FM Architectural/Engineering |  |  | CRAVEN CROFT RENOVATION | Renovation of several Craven Croft Houses to prepare to be rented Estimate prepared by Renovations team | 2020-06-25 15:24 | HORNE, KATHRYN (khorne16) | ROGERS, MICHAEL (mroger59) | VERRET, GREGORY (gverret) | KELLY, SHAWN (skelly64) | 20-0256-I | KELLY, SHAWN (skelly64) | 0 | 0 | 0
IF | 2 | SA-0397 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0503 | Scott Hall | SCOTT HALL TO SOVI BRIDGE | request for FM Projects to evaluate and design a new (replacement) path from Scott Hall Bridge to SOVI (Dining Hall) lower level. | 2018-10-30 15:00 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | KELLY, SHAWN (skelly64) | 19-0072 | KELLY, SHAWN (skelly64) | 10000 | 10000 | 3067.2 | 2019-09-20 | Reviewing Funding will be placed on Hold
IF | 2 | SA-0449 | Approved Scope & Budget PAM | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC BOILER REPLACEMENT | Student Activity Center (SAC) - We are requesting an estimate to replace our boiler unit with an on-demand water heater unit. This unit provides hot water for the showers in the all the locker rooms and dressing rooms. | 2020-01-15 09:21 | BROWN, CURTIS (cbrow307) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | KELLY, SHAWN (skelly64) | 20-0136 | KELLY, SHAWN (skelly64) | 10000 | 0 | 0 |  | Project To Be Placed on Hold to Await Customer Funding
IF | 2 | SA-0451 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0545 | Wallis Hall | WALLIS HALL AIR COOLED CHILLER | For Design Services:The Wallis Hall air cooled chiller is at its end of life. Last summer it actually failed and we had to bring in a temporary chiller to cool the building for a few weeks to the cost of about $40,000. So we'd like to go ahead and | 2020-01-31 07:51 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | KELLY, SHAWN (skelly64) | 20-0161 | KELLY, SHAWN (skelly64) | 200000 | 202500 | 0 | 2020-02-28 | 07/31/20: Projected Construction Completion 08/14/20: Projected Project Closeout Note: Project delayed due to equipment manufacture production delays caused by Covid-19
IF | 0 | SA-0463 | Scope & Budget Requested | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC EAST BOILER REPLACEMENT | BSAC - East Boiler Room, 295A We need options in replacing the boiler in room 295A. We need quotes for a new system with redundancy and quotes on replacing the old system. | 2020-06-29 12:22 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | KELLY, SHAWN (skelly64) | 20-0257-I | KELLY, SHAWN (skelly64) | 0 | 0 | 0
IF | 1 | BA-1824 | Construction | Informal Projects | 12700 | Dept of Materials Management | 0092 | Facilities Ops and Parking (FOPS) | FOPS/RECEIVING INSTALL GATE ACCESS | FOPS - outside wall -- Request card gate access at FOPS wall | 2019-04-11 13:22 | DUNCAN, RANDAL (rduncan1) |  | DUNCAN, RANDAL (rduncan1) | LINGER, JOSHUA (jlinger2) | 19-0205 | LINGER, JOSHUA (jlinger2) | 69336 | 7131 | 6510 | 2020-06-30 | 07/07/2020 - acceptable bid received. working on Purchase Order with customer.
IF | 6 | BA-1854 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0046 | Barnhardt Student Activity Center | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION: Investigate smoke management of SAC during fire alarm activation. AHU devices do not shut down; smoke purge system serving the food court does not function. Assign to Don Janus. | 2019-07-23 08:33 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 20-0034 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | 06/27/20: On Hold Pending Review with Engineering Dept
IF | 2 | BA-1848 | Construction | Informal Projects | 10400 | Business Services AVC | 1010 | South Village Deck | SOUTH VILLAGE DECK WEST ELEVATOR TOWER VENTILATION | SOUTH VILLAGE DECK, provide heating and ventilation in the west elevator tower as per Heapy Engineering recommendations received during the deck reviews (under a Shawn Kelly project). Thanks. | 2019-06-28 11:15 | AVERITT, DREW (daveritt) |  | MULLMANN, JANETTA (jmullman) | LINGER, JOSHUA (jlinger2) | 20-0028 | LINGER, JOSHUA (jlinger2) | 17105 | 188105 | 14424.19 | 2019-12-31 | 07/07/2020 - equipment submittals in review
IF | 2 | BA-1265 | Approved-Design & Estimate PAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM - VERIZON CELLULAR MONOPOLE INSTALL SUPPORT | FPFM: Verizon Project Request to support the expansion and installation of Campus Cellular Service. | 2015-03-09 14:43 | FAKE, WILLIAM (wmfake) | LALIBERTE, RICHARD (rlaliber) | WITHERSPOON, MELANIE (mewither) | LOVE, DAVID (dflove) | 15-0163 | LOVE, DAVID (dflove) | 0.01 | 1510 | 0 | 2020-06-16 | ITS reviewing drawings for new fiber route 1/27/20. Comments will be incorporated into new lease agreement with Verizon. Construction anticipated to start second quarter following lease revisions.
IF | 2 | BA-1471 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0011 | King | KING EMERGENCY POWER SWITCHES | FPFM: King Building: Add Two Emergency Power Automatic Transfer Switches: Per State Electrical Inspector, King Bldg. occupants are at risk; critical life safety features are missing. Point of Contact: Tom MacNab. Assign to Mac Fake. | 2016-08-25 07:43 | FAKE, WILLIAM (wmfake) | CEALLAIGH, SHERRYL (sceallai) | CEALLAIGH, SHERRYL (sceallai) | LOVE, DAVID (dflove) | 17-0036 | LOVE, DAVID (dflove) | 54800 | 54800 | 9249.95 | 2017-04-28 | Designer construction document revisions ongoing. Bidding to follow with anticipated construction starting following commencement.
IF | 2 | BA-1747 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 1007 | Union Deck | UNION DECK BLUE LIGHT PHONES | UNION DECK Blue Light Phones, add additional blue light phones.Per 10/17/18 email from Troy Russell - the two dead emg phones on the 6th level of the existing deck have been removed until project replaces them along with the existing stairwell #2.Als | 2018-10-17 15:36 | AVERITT, DREW (daveritt) |  | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0095 | LOVE, DAVID (dflove) | 0 | 0 | 0 |  | Met with customer and Risk Management to establish scope. S&B in progress at 60%.
IF | 6 | BA-1889 | Project On Hold Design Services | Informal Projects | 13115 | Safety and Security | 0046 | Barnhardt Student Activity Center | FIRST PRIORITY CAMERA PROJECT PHASE 2 | Please assign to David Love - Phase 2 includes SAC, West Deck, Belk Gym, Cone, Colvard, Levine Hall, Cato, Prospector, McEniry, Auxiliary Services, Cameron, Bioinformatics, PORTAL, EPIC, Grigg, Duke, Motorsports, South Village Deck. (Approximately 2 | 2020-01-07 10:31 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | SPATARO, EVAMARIE (espataro) | 20-0115 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Defining Scope & Timeline with Customer. On hold until priority 1 is complete.
IF | 2 | BA-1796 | Req Scope & Budget Review | Informal Projects | 10400 | Business Services AVC | 1008 | North Deck | NORTH DECK FFA LIGHTING REPLACEMENT | NORTH DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:30 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0161 | LOVE, DAVID (dflove) | 7900 | 0 | 0 |  | Project will move forward pending the new campus standard LED light fixture approval. Existing standard is no longer being manufactured.
IF | 6 | BA-1913 | Project On Hold FAM | Informal Projects | 13115 | Safety and Security | 0000 | Campus | CAMPUS SIREN UPGRADE "ALERTUS" | Safety & Security - Campus Siren upgrade - "Alertus" | 2020-01-31 11:09 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | LOVE, DAVID (dflove) | 20-0162 | LOVE, DAVID (dflove) | 0 | 0 | 0
IF | 2 | BA-1797 | Req Scope & Budget Review | Informal Projects | 10400 | Business Services AVC | 1009 | CRI Deck 1 | CRI DECK FFA LIGHTING REPLACEMENT | CRI DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:31 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0162 | LOVE, DAVID (dflove) | 6800 | 0 | 0 |  | Project will move forward pending the new campus standard LED light fixture approval. Existing standard is no longer being manufactured.
IF | 1 | BA-1830 | In Design | Informal Projects | 13115 | Safety and Security | 0055 | Facilities Management & Police & Public Safety | FM & POLICE BLDG - RM 281 - RADIO INFRASTRUCTURE | FM & Police Building - Room 281 - Radio Infrastructure Upgrade | 2019-05-08 10:22 | HILL, MICHELLE (mphilipp) | BARNES, RICKY (rbarne29) | BARNETT, DENISE (dbarne33) | LOVE, DAVID (dflove) | 19-0219 | LOVE, DAVID (dflove) | 163120 | 0 | 0 |  | (02/05/20) - Site walk with engineers for formal design proposals completed. Motorola revising proposal following results from site survey. Revised Design cost to be submitted for customer review mid February.
IF | 6 | BA-1944 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | STARBUCKS TRUCK PAD AND ELECTRICAL | STARBUCKS TRUCK Pad and Electrical, provide design to provide a prototypical pad off off the sidewalk for Starbucks Truck to pull over and sell during the day. Initial location is intended to be Smith but pad could be used anywhere - need pull off, | 2020-04-10 12:56 | AVERITT, DREW (daveritt) | THOMPSON, JODY (jthom373) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0221-I | SMITH, RYAN (rsmit341) | 26000 | 0 | 0 |  | Project on Hold per DA per 6/16/2020 Email
IF | 1 | AA-1567 | Construction | Informal Projects | 17800 | Art & Art History | 0019 | Rowe | ROWE 265, 268B, 268E & 269 VENTILATION IM | Rowe Arts - 265, 268B, 268E, 269 -As described in previous agreements, with Design Services, to improve the ventilation in the Photography Labs in Rowe, for the Department of Art + Art History to meet NASAD accreditation requirements, four areas in R | 2018-12-05 18:17 | SCHAUBLE, DONIA (dcooke) |  | HUNTER, KATHY (kdwhaley) | SMITH, RYAN (rsmit341) | 19-0088 | SMITH, RYAN (rsmit341) | 8000 | 208062 | 113493.57 | 2019-06-30 | 7/13/20: Continue Construction 7/31/20: Construction Complete 08/28/20: Projected Project Closeout
IF | 1 | AA-1603 | Construction | Informal Projects | 15210 | Col of Arts & Architecture | 0019 | Rowe | ROWE - FUME VENTING 289, 291, 297, 298 | Rowe Arts - 289, 291, 297, 298 - The advanced project labs in Rowe need dedicated venting. Each room needs to be able to control the system. Budget allocation is around $20,000 (from AA - see Dr. Raja). If funds do not match work needed, rooms should | 2019-03-22 10:41 | SCHAUBLE, DONIA (dcooke) |  | HUNTER, KATHY (kdwhaley) | SMITH, RYAN (rsmit341) | 19-0183 | SMITH, RYAN (rsmit341) | 7800 | 60000 | 23906.56 | 2019-10-31 | 7/13/20: Continue Construction 7/31/20: Construction Complete 08/28/20: Projected Project Closeout
IF | 0 | AA-1709 | Construction | Informal Projects | 24202 | OneIT-Enterprise Infrastructure | 0004 | Atkins | ATKINS L36 G20 UPS | Atkins UPS for Atkins L-36 and G20ITS would like to start a project to replace the existing UPS at Atkins for our IT rooms. We have been in conversation with Tom MacNab who has worked with a vendor to provide a quote for what he feels is needed bas | 2020-04-27 07:30 | FRANCUS, KATHLEEN (krfrancu) | FRANCUS, KATHLEEN (krfrancu) | VITALLO, JUDY (jvitallo) | SMITH, RYAN (rsmit341) | 20-0229-I | SMITH, RYAN (rsmit341) | 10000 | 44800 | 0 | 2020-09-30 | 7/13/20: Issue Consultant PO
IF | 2 | BA-1864 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR REROOF UPPER LEVEL | PROSPECTOR Reroof Upper Prospector - remove and replace the Upper Prospector roof which is only area that is still rubber and rock ballast with EPDM roof to match newer areas. | 2019-10-28 11:59 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0090 | SMITH, RYAN (rsmit341) | 26502 | 26502 | 13000 | 2020-03-13 | 7/20/20: Begin Construction 8/31/20: Construction Complete
IF | 2 | BA-1903 | Construction | Informal Projects | 10400 | Business Services AVC | 1096 | Chancellor's Lot | CHANCELLOR'S LOT CRACK SEAL & SEAL COAT | CHANCELLOR'S LOT CRACK SEAL & SEAL COAT, utilize JSS's existing contract to provide crack seal and seal coat maintenance this summer | 2020-01-23 09:17 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0146 | SMITH, RYAN (rsmit341) | 8600 | 8600 | 0 | 2020-04-03 | 7/13/20: Begin Work 08/31/20: Project Closeout
IF | 0 | BA-1951 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | PARKING DECK REPAIR YEAR 2; FACADE | PARKING DECK REPAIR Year 2; Facade, Joint & Concrete RepairYear 2 regular maintenance as specified by 5 year parking deck maintenance plan for repair of concrete flooring, exterior masonry, expansion joints, crack sealant, and facade repair. | 2020-04-27 07:31 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0231-I | SMITH, RYAN (rsmit341) | 150000 | 150000 | 83565.47 | 2020-08-31 | 7/13/20: Continue Construction 8/31/20: Construction Complete 9/31/20: Project Closeout
IF | 0 | BA-1952 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | PARKING DECK REPAIR YEAR 2; ROOF, SLAB | PARKING DECK REPAIR Year 2; Roof, Slab & Grout PocketScope of Work: Year 2 regular maintenance as specified by 5 year parking deck maintenance plan for roof, slab, grout pocket, and other misc repairs. | 2020-04-27 07:31 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0232-I | SMITH, RYAN (rsmit341) | 250000 | 250000 | 91700.86 | 2020-08-31 | 7/13/20: Continue Construction 8/31/20: Construction Complete 9/31/20: Project Closeout
IF | 0 | BA-1954 | Construction | Informal Projects | 10400 | Business Services AVC | 1004 | East Deck 2 | EAST DECK 2 REPAIR SPRINKLER STAND PIPE | EAST DECK 2 REPAIR SPRINKLER STAND PIPE, the standpipe hose fire protection system leaked profusely during recent 5 year hydrostatic testing. Repair the system with bypass piping to avoid the underground leaks with above ground piping, including FDC | 2020-04-29 10:11 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0235-I | SMITH, RYAN (rsmit341) | 129500 | 129500 | 0 | 2020-12-01 | 7/13/20: Solicit bids
IF | 0 | BA-1955 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR REPLACE AHU-3 | PROSPECTOR REPLACE AHU-3. Replace AHU-3 which recently had the motor go down. Unit is 32 years old and probably best to make a full replacement rather than just the motor. Don Janus has been involved in discussions. | 2020-05-06 07:35 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0236-I | SMITH, RYAN (rsmit341) | 240500 | 240500 | 6000 | 2020-10-01 | 7/15/20: Begin Construction (Periphery Work) 9/1/20: AHU Delivered 10/1/20: Construction Complete/Begin Commissioning
IF | 0 | BA-1960 | Construction | Informal Projects | 10500 | Auxiliary Operations | 1005 | West Deck | WEST DECK ARROWS | West Deck - repaint arrows Call West deck arrows) | 2020-05-13 11:06 | HOLMES, ROBERT (rholme16) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0241-I | SMITH, RYAN (rsmit341) | 4020 | 4020 | 0 | 2020-08-30 | 100% complete project closeout phaset
IF | 0 | BA-1961 | Construction | Informal Projects | 10500 | Auxiliary Operations | 1004 | East Deck 2 | EAST DECK 2 ARROWS | East 2 - remove replace thermo arrows East 2 - restripe entire deck | 2020-05-13 11:27 | HOLMES, ROBERT (rholme16) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0242-I | SMITH, RYAN (rsmit341) | 23000 | 23000 | 22860 | 2020-08-30 | 100% complete project closeout phase
IF | 0 | BA-1962 | Construction | Informal Projects | 10500 | Auxiliary Operations | 1006 | East Deck 3 | EAST DECK 3 RESTRIPING | East 3 - re stripe level 5 and level 5 ramp (call East deck 3 | 2020-05-13 11:28 | HOLMES, ROBERT (rholme16) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0243-I | SMITH, RYAN (rsmit341) | 4200 | 4200 | 4105 | 2020-08-30 | 100% complete project closeout phase
IF | 2 | BA-1756 | In Design | Informal Projects | 10400 | Business Services AVC | 1009 | CRI Deck 1 | CRI DECK ELECTRICAL REPAIRS | CRI DECK, Electrical Repairs, the bulk of the raceways in the main electrical closet exit the panelboards on the top, with the exception of the genset battery charger / jacket heater circuit. This circuit is in the slab of the electrical room, and c | 2018-12-13 11:34 | HOLMES, ROBERT (rholme16) |  | MULLMANN, JANETTA (jmullman) | SPATARO, EVAMARIE (espataro) | 19-0097 | SPATARO, EVAMARIE (espataro) | 35000 | 0 | 0 |  | (7/7/2020) Waiting on engineering to review exemption request
IF | 6 | SA-0444 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE NORTH ROOF REPLACEMENT | Cone North Roof Replacement - Fully remove existing system to replace the Cone North Building Roofing System. | 2019-12-09 13:04 | MERCK, DONNA (dlmerck) |  | HARRIS, MELODY (mhharris) | BOAL, JOHN (jboal1) | 20-0112 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 6-23-2020: Project on hold.
IF | 2 | BA-1792 | Construction | Informal Projects | 10400 | Business Services AVC | 1005 | West Deck | WEST DECK ELECTRICAL ROOM REPAIRS | WEST DECK Electrical Room Repairs, review, determine and provide electrical room repairs and upgrades to prevent water penetration and or corrosion that is occurring. Thanks Drew 7-8653. | 2019-02-08 08:48 | AVERITT, DREW (daveritt) |  | MULLMANN, JANETTA (jmullman) | SPATARO, EVAMARIE (espataro) | 19-0153 | SPATARO, EVAMARIE (espataro) | 5500 | 67200 | 16776.92 | 2019-12-31 | (7/7/2020) Electrical completed and billed. Plumbing underway. All construction to be complete by 7/20.
IF | 1 | BA-1888 | Construction | Informal Projects | 13115 | Safety and Security | 0545 | Wallis Hall | FIRST PRIORITY CAMERA PROJECT PHASE 1 | Please assign to David Love - Phase 1 includes the 4 designated sections A1, A2, A3, & A4. The buildings this includes is Wallis Hall, Lynch Hall, Student Union, CHHS, COE, SAC, Cone, Atkins Library, Kennedy, Fretwell, Friday, Cato, Denny, & Winning | 2020-01-07 10:18 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | SPATARO, EVAMARIE (espataro) | 20-0114 | SPATARO, EVAMARIE (espataro) | 200000 | 200000 | 0 | 2020-08-31 | (7/7/2020) Cameras currently being mounted. Additional cameras be ordered. Still in budget. Still on schedule for end of August.
IF | 2 | SA-0435 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0078 | Judy W. Rose Football Center | JUDY ROSE FOOTBALL CENTER -BOILER DUCTS | Condensate is leaking from the boiler ducts in the building. Please hire a contractor to repair damaged duct and provide other drainage solutions for the system. All work must be scheduled around event usage of the building. | 2019-09-16 09:51 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | SPATARO, EVAMARIE (espataro) | 20-0076 | SPATARO, EVAMARIE (espataro) | 11000 | 88000 | 82216.67 | 2020-03-31 | (7/7/2020) Complete. Waiting on accounting to finish processing invoices to close.
SA | 2 | SA-0425 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0029 | Housing and Residence Life | ELM, MAPLE & PINE METER INSTALL | Can you please put in a project request for design services.Install meters and integrate into BAS at Elm, Maple and Pine hall. | 2019-07-25 11:00 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | BOAL, JOHN (jboal1) | 20-0036 | BOAL, JOHN (jboal1) | 20637.8 | 20637.8 | 20637.8 | 2019-08-15 | 6-23-2020: Meters have been installed. Start up and testing are being scheduled now.
SA | 2 | SA-0436 | Construction | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 251 SUITE RENO FF&E | Separation of FF&E funds for SU 251 renovation project with Amanda Caudle. | 2019-10-04 15:37 | MEEHAN, MORGAN (mmeeha11) |  | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 20-0067 | CAUDLE, AMANDA (afelock) | 345000 | 407000 | 398386.95 | 2019-10-10 | (7-14-20) Project approx. 98% complete. Wrapping up punch list items.
SA | 2 | SA-0443 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0564 | Martin Hall | MARTIN HALL SHOWER REPLACEMENT FY20 | Please put in an Archibus request for Design Services. We want to demo existing and install 50 new solid surface shower surrounds in Martin Hall, similar to the work that has been done in there during the previous years. Thanks! Donny | 2019-12-04 11:13 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | CAUDLE, AMANDA (afelock) | 20-0097 | CAUDLE, AMANDA (afelock) | 230000 | 230000 | 154778.62 | 2019-12-17 | (7-14-20) PO issued 2-17-20. Work began May 11 and complete by early August.
SA | 2 | SA-0456 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION COMMAND CENTER SPEAKER SYSTEM | Student Union wants to use a command center speaker utilized through current Fire Control Panel for Building Announcements. | 2020-02-18 16:55 | BROWN, JOSHUA (jbrow450) |  | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 20-0187 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Under review with Engineering Services and Fire Systems.
SA | 6 | SA-0388 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC ARENA BB & CURTAIN - LOW VOLTAGE | Change existing retractable basketball goals and mechanical partition curtain systems in Halton arena from 120v to low voltage. | 2018-07-26 14:21 | MOON, STUART (sgmoon) |  | BARNES, TRENT (tbarne21) | SPATARO, EVAMARIE (espataro) | 19-0038 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) On hold.
SA | 6 | SA-0407 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0077 | Halton-Wagner Tennis Complex | HALTON TENNIS COMPLEX LOWER HALL FLOODING | The lower hallways of the Halton Tennis Complex flood when there is heavy rain. Zone 1 has performed some modifications to the weep holes in the brick which has helped but we are still getting some flooding. The water drains towards the building inst | 2019-01-24 16:57 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 19-0134 | LANIER, LISA (llanier) | 34000 | 0 | 0 |  | 02-13-2020 Discussed project with Cass Ferguson. Project does not have funding at this time. Needs further discussion due to continued water infiltration. Does not appear to be site related.
SA | 6 | SA-0408 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE SOUTH 3 MODERNIZATION | Cone Center - South 3: Upgrade and modernize South 3 level of Cone Center. Collaborate with Director and Associate Director to establish design options and features. | 2019-01-31 13:53 | MERCK, DONNA (dlmerck) |  | MERCK, DONNA (dlmerck) | CAUDLE, AMANDA (afelock) | 19-0147 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) On hold - waiting for Morgan and Donna to provide scope of work
SA | 0 | SA-0467 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION PLUMBING DRAIN LINES STUDY | A project to fully investigate these apparent systemic issues and provide recommendations to bring the system into reliable operating conditions. Can original construction team involvement for repair/remediation/cost recovery? We would like the fee | 2020-07-08 08:04 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | CAUDLE, AMANDA (afelock) | 21-0005-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Meeting scheduled for Tuesday, July 21 at 10am for engineer walk thru to develop fee proposal.
SA | 2 | SA-0365 | Construction | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 2ND FLOOR CARPET REPLACEMENT | Replace the carpet in 2nd floor common areas of the student union. Well worn areas include by the stairwell and Crown Commons | 2018-02-14 12:47 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | HARRIS, MELODY (mhharris) | HILL, CAROLINE (cmhill2) | 18-0146 | HILL, CAROLINE (cmhill2) | 135100 | 135100 | 117397.75 | 2019-01-30 | 6/29/2020 - Working through punch list items. Will turn invoices in soon.
SA | 6 | SA-0424 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION LED LIGHTING RETROFIT | Student Union - Entire BuildingStudent Union wants to increase sustainability by reducing energy consumption and decrease annual maintenance cost for replacement fluorescent lights by retrofitting lighting to LED. This project aligns with UNC policy | 2019-06-24 09:37 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | SPATARO, EVAMARIE (espataro) | 20-0022 | SPATARO, EVAMARIE (espataro) | 43000 | 0 | 0 |  | (7/7/2020) On hold.
SA | 2 | SA-0372 | Construction | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE 382 RENOVATION FOR OFSL | Review and provide drawing for update to OFSL Suite (382) in Cone Center. Would like to maximize space efficiency. | 2018-03-14 12:00 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | HARRIS, MELODY (mhharris) | HILL, CAROLINE (cmhill2) | 18-0184 | HILL, CAROLINE (cmhill2) | 23700 | 172195.35 | 166705.94 | 2019-08-31 | 6/29/2020 - Working on submitting final invoicing.
SA | 2 | SA-0409 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 200 UPGRADES | Student Union - 200 - Aesthetic and other upgrades to room 200 to reflect new naming of space as James M. Hoppa Room. | 2019-02-12 13:12 | MEEHAN, MORGAN (mmeeha11) | BROWN, JOSHUA (jbrow450) | MARTIN, KAREN (kmart126) | HILL, CAROLINE (cmhill2) | 19-0156 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Working with customers on finish selection and pulling scope & budget together.
SA | 6 | SA-0439 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 062 FITNESS ROOM RENOVATION | Fitness room renovation two include two spaces; one space is to remain a multipurpose room for events and the other space is to be converted into offices and storage space. Would like to keep as much of original hardwood floor as possible. | 2019-10-09 09:37 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | LINGER, JOSHUA (jlinger2) | 20-0070 | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 |  | 07/07/2020 -Project on hold while Customer determines if they have other options.
SA | 6 | SA-0440 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 334A-E SALONS LIGHTING UPDATE | Replace light fixtures, and update control system to accommodate new lighting. | 2019-10-09 09:42 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | SPATARO, EVAMARIE (espataro) | 20-0071 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (6/30/2020) Project can be FF&E. Will work with customer to schedule. Customer holding for funding.
SA | 6 | SA-0441 | Project On Hold Design Services | Informal Projects | 28900 | University Recreation | 0017 | Belk Gymnasium | BELK GYM 127 RECONFIGURE | Adding a door and wall to create a designated space to be used after UREC moves from Belk Gym to UREC building. Separating COR10 from 127 | 2019-10-16 13:31 | BELL, ROBERT (rbell16) |  | BARRETT, LACRISSA (lbarre11) | LINGER, JOSHUA (jlinger2) | 20-0074 | LINGER, JOSHUA (jlinger2) | 9987.5 | 0 | 0 |  | 07/07/2020 -Project on Hold per email from Robbie Bell 02/24/20. Overall price ($9,988) was more then they expected. They will use the space as is for now to determine necessity of project.
SA | 6 | SA-0442 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0017 | Belk Gymnasium | BELK GYM 120 VENTURE MOVE | Venture has been approved to move from Cone to Belk gym. Within this project includes: coordinating a move of the staff, office furnishing needs, space renovations in Belk for storage space. As this project is related to project SA-0441 it could be | 2019-10-24 14:09 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | WELLS, ALICIA (awells43) | 20-0080 | WELLS, ALICIA (awells43) | 160000 | 160000 | 0 | 2020-07-31 | (6/23/20) Project ready for order placement but on hold until FY21
SA | 2 | SA-0411 | Construction | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 150 NORMS UPGRADES | Student Union - 150 - Upgrades to furniture, gaming equipment, technology in Norms space in the Student Union | 2019-02-13 15:34 | MEEHAN, MORGAN (mmeeha11) | BROWN, JOSHUA (jbrow450) | DALE, JEREMY (jdale8) | HILL, CAROLINE (cmhill2) | 19-0160 | HILL, CAROLINE (cmhill2) | 2800 | 2800 | 2360.5 | 2020-06-30 | 6/29/2020 - Waiting on Customers to approve funding to be able to submit purchase orders.
SA | 1 | IA-0035 | Construction | Informal Projects | 30900 | Athletics Admin/Support | 0046 | Barnhardt Student Activity Center | SAC 066 ATHLETIC WEIGHT ROOM RENOVATION | Building Name - Barnhardt Student Activity CenterRoom Number - 066Will need to add three offices to weight room in the SAC when Recreation vacates the area in November. Cannot do project until UREC has vacated the area after 11/1. | 2019-06-05 16:33 | FERGUSON, JAMES (jcfergus) |  | SPEASE, DARIN (dspease) | LINGER, JOSHUA (jlinger2) | 20-0053 | LINGER, JOSHUA (jlinger2) | 28500 | 114500 | 49150.78 | 2020-05-29 | 07/07/2020 construction continues.
SA | 6 | SA-0450 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION M101 ESPORTS LOUNGE | There is a space identified in the Student Union as a potential opportunity for an Esports Lounge. Need to determine if it is feasible in the space given the needs of the group. Need feasibility information by 1/28 and then will proceed further if ne | 2020-01-16 10:59 | MEEHAN, MORGAN (mmeeha11) |  | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 20-0137 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-14-20) Informal budget provided to Morgan Meehan 1-27-20. Pending approval to proceed. Placed on Hold April 27.
SA | 6 | SA-0454 | Project On Hold Design Services | Informal Projects | 29700 | Housing and Residence Life | 0544 | Witherspoon | WITHERSPOON CABINET & COUNTERTOP REPLACEMENT | Witherspoon Hall.. We want to replace the countertops and cabinets in the kitchens in similar configuration to what's currently in the apartments. ..per Alan Hinton 757-692-9020 | 2020-02-11 15:47 | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | LINGER, JOSHUA (jlinger2) | 20-0173 | LINGER, JOSHUA (jlinger2) | 353194.69 | 0 | 0 |  | 07/07/2020 - project on hold due to cost considerations
SA | 6 | SA-0455 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 340 POWER UPGRADE | Student Union would like to add additional power to the multi purpose room 340. We are looking at 100A, 3 phase, 5 wire, 120/208V. Requesting Eva Spataro on this project | 2020-02-18 16:03 | BROWN, JOSHUA (jbrow450) |  | MEEHAN, MORGAN (mmeeha11) | SPATARO, EVAMARIE (espataro) | 20-0186 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Sent scope and budget to customer. Customer taking S&B to lobby for funding.
SA | 0 | IA-0036 | Scope & Budget Requested | Informal Projects | 30900 | Athletics Admin/Support | 0078 | Judy W. Rose Football Center | FOOTBALL LOCKER REPLACEMENT | Judy Rose Fieldhouse - Home Football Locker RoomTo replace lockers in home football locker room. Athletics has secured the lockers they want to purchase but need project # so that SCO can approve any electrical needs. Have discussed with Lisa Lanier. | 2020-05-18 11:38 | FERGUSON, JAMES (jcfergus) | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) | LINGER, JOSHUA (jlinger2) | 20-0246-I | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 |  | 07/07/2020 - finalizing SCO drawings for submission.
SA | 2 | SA-0447 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0560 | Resident Managers House | GREEK HOUSE 14 CAMERA | Can you please create a design service project for pulling wiring and adding in an electrical outlet at Greek House 14 (Resident Manager's House) for the camera project?Thanks,Donny | 2019-12-12 12:10 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | LINGER, JOSHUA (jlinger2) | 20-0109 | LINGER, JOSHUA (jlinger2) | 8000 | 38500 | 0 | 2020-07-31 | 07/07/2020 - HVAC complete. Waiting on electrical panel. Final electrical inspection tentatively scheduled for July 14.
SA | 2 | SA-0459 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0544 | Witherspoon | WITHERSPOON FALLING KEYSTONES | Please put in an Archibus request for Design Services. We have some failing keystones underneath a few balconies at Witherspoon Hall and need some help determining the proper fix.Thanks,Donny | 2020-02-26 15:19 | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | LINGER, JOSHUA (jlinger2) | 20-0189 | LINGER, JOSHUA (jlinger2) | 15537.5 | 20037.5 | 4670 | 2020-08-28 | 07/07/2020 - Existing installation reviewed. Waiting on design solution from engineer.
SA | 0 | SA-0464 | Scope & Budget Requested | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC ATAC GLASS ROOF REPAIR | BSAC-ATAC We need a roof contractor to evaluate the glass roof in the ATAC practice gym hallway and find a solution to stop the multiple leaks stemming from bad pressure plates that are no longer stopping the water. | 2020-06-29 14:42 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | LINGER, JOSHUA (jlinger2) | 20-0260-I | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 |  | 07/07/2020 Reviewing scope with Renovations
SA | 0 | SA-0465 | Scope & Budget Requested | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC OFFICE LEAK ROOM 303 | BSAC - Room 303. There is a substantial leak in office 303 but upon prior inspections the leak does not seem to come from the roof but perhaps issues with the gutter system or the window panes. We need a contractor to evaluate the source of the probl | 2020-06-29 14:42 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | LINGER, JOSHUA (jlinger2) | 20-0261-I | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 |  | 07/07/2020 Reviewing scope with renovations.
SA | 6 | SA-0462 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS AND PREFUNCTION CARPET | Project is to gather estimates and designs on replacing the carpet inside and outside of the SAC Salons. | 2020-03-16 08:40 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | HILL, CAROLINE (cmhill2) | 20-0202-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Customer would like to wait until we return to campus to proceed with project.
SA | 0 | SA-0468 | Scope & Budget Requested | Informal Projects | 29700 | Housing and Residence Life | 0503 | Scott Hall | SCOTT & HOLSHOUSER FIRE ALARM MODIFICATIONS | I am requesting a project to modify the fire alarm system to utilize lounges in Scott Hall and Holshouser Hall as overflow / temporary housing for students to start the fall semester. This will likely require a submission to SCO. Thanks, Donny | 2020-07-08 10:04 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | LINGER, JOSHUA (jlinger2) | 21-0006-I | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0
SA | 2 | SA-0458 | Construction | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE MCKNIGHT HALL LIGHTING UPGRADE | Cone McKnight Hall Room 320 - Replace house and theater lighting; and replace the Stage curtain with similar grade fabric. | 2020-02-21 14:06 | MERCK, DONNA (dlmerck) | MERCK, DONNA (dlmerck) | MEEHAN, MORGAN (mmeeha11) | SPATARO, EVAMARIE (espataro) | 20-0188 | SPATARO, EVAMARIE (espataro) | 285000 | 285000 | 0 | 2020-08-31 | (6/30/2020) Design documents being reviewed by engineering
SA | 2 | SA-0461 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS A/V | Project is to replace and upgrade Salon A/V. Project would include replacement of projectors and screens, additional projectors and screens, increased capability of streaming and conferencing, integration of cable TV, and necessary upgrades to audio | 2020-03-16 08:39 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | SPATARO, EVAMARIE (espataro) | 20-0201-I | SPATARO, EVAMARIE (espataro) | 25000 | 25000 | 0 | 2020-08-31 | (7/7/2020) Design review meeting on Thursday
SA | 2 | SA-0457 | Req Scope & Budget Review | Informal Projects | 30000 | Health Services | 0065 | Student Health Center | SHC OUTDOOR BUILDING SIGNS | Project request for outdoor building signage. | 2020-02-19 08:43 | FLORES, CLAUDIA (cflores3) | SIMPSON, BRANDI (BrandiSimpson) | BARRETT, LACRISSA (lbarre11) | TERRY, STEPHEN (slterry) | 20-0218-I | TERRY, STEPHEN (slterry) | 13500 | 0 | 0 |  | 06-03-20. No change. Budget review. Customer said to hold.
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | SCIENCE BUILDING | The Science Building will provide important undergraduate class laboratory and interdisciplinary research space for UNC Charlotte. Many of UNC Charlottes buildings were constructed before doctoral instruction and, in some cases, before master leveli | 2011-06-02 09:30 | RAJA, JAYARAMAN (jraja) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 90000000 | 96854877.13 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | McEniry Chiller Replacement |  | 2020-06-11 |  | JANUS III, DONALD (drjanus) | WITHERSPOON, MELANIE (mewither) |  | 20-0264-F |  | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0000 | Campus | FO - FACILITIES OPERATIONS COMPLEX | The current Facilities Operations building is located on the proposed site of the new Science building. A new Facilities Operations building (32,000 square feet) must be constructed in order for the existing facility to be demolished. A new Receiving | 2011-06-02 15:57 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 24298000 | 22845568.77 | 0
| 0 |  | Created | Capital Projects | 29700 | Housing and Residence Life | 0543 | Elm | Elm, Maple, Pine Renovation | Needed renovations. Buildings must open by Fall 2015. | 2012-02-13 10:29 | STORCH, JOHN (jdstorch) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | NEILSON, JOHN (jneilson) | 0 | 20318633.39 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | East Village Infrastructure | East Village infrastructure including Martin Village Road re-alignment, Van Landingham bridge, lighting, telelcom, storm, sanitary and the electrical extension to the campus substation. Includes a traffic signal at John Kirk Drive. | 2013-10-08 08:26 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 4135056.7 | 7306234.75 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | WEST SUBSTATION | Project adds a second electrical substation to feed electricity from Duke Energy 100 KVA supply on the west side of campus (across W.T. Harris). This is needed to provide redundancy to our electrical source to insure fail safe operation for research | 2013-10-08 10:19 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 6500000 | 2539400.2 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | CAMPUS STORM WATER PROJECT - PHASE II | Authorization is $850,000 - Capital budget is $750,000. Storm Water Volume Control r-58. #2 priority project in Storm Water Master plan. Required to bring us into compliance with Clean Water Act.The restoration of Toby Creek is proposed as a partners | 2013-12-16 16:34 | FESSLER, JOHN (jafessle) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 750000 | 342859.45 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | ACADEMIC COMPLEX | Facilities conditions improvements and renovation over Garinger, Barnard, Denny, Macy and Winningham. | 2014-07-23 10:46 | MANDERINO, LAUREL (lmanderi) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 3702000 | 20523251.22 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0537 | Sycamore | SYCAMORE - Hall Renovation | Sycamore Hall was completed in 1981as a residence hall. A study conducted in 2012 indicated that it is not cost effective to renovate the structure as a residence hall and a subsequent sector study slated it for demolition. As space is needed on cam | 2014-10-07 10:14 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 3898232.3 | 5284123.76 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | EAST VILLAGE UTILITIES | The project is for the construction of utility infrastructure to support improvements to the East Village sector of campus to include water, telecom, and high voltage electrical service. | 2015-03-12 09:37 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 2100000 | 1279159.45 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | ADMISSIONS AND VISITORS CENTER | This project is to construct a new Admissions and Visitors Center on campus. The Admissions and Visitors Center is intended to welcome prospective students and their families to campus, house undergraduate admissions offices, and serve as a startingp | 2015-11-02 11:38 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 7000000 | 8371352.18 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 1057 | Lot 8 | LOT 8 - PARKING EXPANSION | Lot 8 expansion will provide additional parking for South Village. The expansion will support the Admissions and Welcome Center with dedicated spaces for these functions. It will also provide additional parking needed by residents in and staff of L | 2016-03-15 08:22 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 475000 | 813480.05 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0004 | Atkins | ATKINS CAREER CENTER RENOVATION | The University Career Center, located in Atkins Library, does not have sufficient space to serve UNC Charlotte's growing student population. Additionally, the quality and configuration of the current space is inadequate. This project will renovatet | 2016-03-23 09:40 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 2000000 | 1830000 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0046 | Barnhardt Student Activity Center | STUDENT ACTIVITY CENTER (SAC) IT UPGRADE | This project provides for information technology (IT) upgrades in the Student Activities Center and Miltimore-Wallis Athletic Center. The network wiring, electrical, and cooling will be enhanced. The current network cabling is past its normal lifeex | 2016-12-14 10:41 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | NEILSON, JOHN (jneilson) | 1400000 | 1478573.24 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0069 | Popp Martin Student Union | STUDENT UNION - CROWN COMMONS RENOVATION | The Student Union was completed in 2009. The 9300 SF "Crown Commons" Dining Facility is a highly trafficked area utilized by thousand of patron daily. By the time this project occurs, the facility will be 10 years old and will need renovations includ | 2016-12-14 11:25 |  |  | PAQUETTE, NOELLA (njpaquet) |  |  |  | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | RECLAIMED WATER | The University has developed a proposed partnership with Charlotte Water (City of Charlotte) to bring reclaimed water to campus from the Mallard Creek waste water plant. This water will replace potable water currently used in chillers and boilers on | 2016-12-15 07:53 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 2100000 | 1965355.27 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0043 | Wells Fargo Fieldhouse | WELLS FARGO SOFTBALL INDOOR TRAINING FACILITY | A new Softball Indoor Training facility will be constructed in order to improve and extend practice schedules to remain competitive with other collegiate women's softball programs, including Conference USA peers. Further, the project will result in c | 2017-05-25 08:46 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | NEILSON, JOHN (jneilson) | 650000 | 1174971.62 | 0
| 0 |  | Created | Capital Projects | 29700 | Housing and Residence Life | 0501 | Moore Hall | RESIDENCE HALL XVI | Demolition of Moore and Sanford Halls and construction of new 750-800 bed residence hall in South Village. | 2017-11-07 09:21 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | NEILSON, JOHN (jneilson) | 58006748 | 60903202.85 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | STUDENT GOVERNMENT OFFICE RENOVATIONS | Student Government Office Complex (2nd floor) renovation to allow students to see activities going on in the space from outside the suite and better use of space. | 2018-02-12 09:53 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 1210502.76 | 1102723.5 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0017 | Belk Gymnasium | INTERCOLLEGIATE SWIMMING UPFIT | Renovation of space in Belk Gym to provide coaches offices, a locker room, training room and team meeting room. The existing pool will be modified to meet NCAA regulations. | 2018-06-01 14:21 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 3505005.91 | 3343940.97 | 0
| 0 |  | Created | Capital Projects | 15100 | Academic Affairs VC | 0068 | Bioinformatics | BIOINFORMATICS 4TH FLOOR UPFIT | Build-out 4th floor to provide interdisciplinary research space to support UNC Charlotte's need for labs and faculty offices. | 2018-06-04 10:33 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 10500000 | 9367077.83 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | CAMPUS - ROOF REPAIRS AND REPLACEMENT | This project will address needed roof repairs and replacements for Atkins Library, Storrs, and Memorial Hall. | 2018-09-28 08:24 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 1300000.01 | 1427365.08 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | CAMPUS - HVAC SYSTEM REPAIRS AND UPGRADES | This project will address needed HVAC repairs and upgrades in McEniry. | 2018-09-28 08:28 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 500518.85 | 1236313.66 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | INFORMATION TECHNOLOGY INFRASTRUCTURE UPGRADES | IT Infrastructure Upgrades in Rowe, Storrs and Reese | 2018-10-18 11:02 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 3800050.24 | 3140199.43 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | HOTEL CONSTRUCTION ROAD | The Hotel Construction Road project will build a temporary construction entrance from North Tryon to CRI Lot 2. This road will be used in the short term by the Hotel contractor to place fill at a building site behind Motorsports II. In the long ter | 2019-03-27 08:21 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | KUGLER, BRIAN (bhkugler) | 235004 | 243859.38 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0042 | Cameron Hall | CAMERON SECOND FLOOR RENOVATION | The second floor of Cameron will be renovated to provide space for chemistry research labs. | 2019-06-03 13:14 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 1950000 | 18306959 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 1054 | Lot 5A | LOT 5A | re-alignment of lot 5A | 2019-11-19 14:10 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 702248.85 | 742025 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0020 | McEniry | MCENIRY HVAC PHASE 4 | Replace HVAC in McEniry | 2019-11-19 15:06 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | BOAL, JOHN (jboal1) | 7336875 | 9612797.05 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0000 | Campus | CRI ENTRANCE ROAD | Create a new entrance off Hwy 29 | 2019-11-20 05:15 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 1449300 | 1159589.44 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0045 | Fretwell | FRETWELL CAFE' RENOVATION | Renovate Fretwell Cafe' | 2019-11-20 05:38 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | SISCO, ASHLEY (asisco1) | 722500 | 722500 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | POPP MARTIN STUDENT UNION | renovate Einsteins, New Venue & Crown Commons | 2019-11-20 05:53 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 9638114.5 | 9111644 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0097 | Science Building | SCIENCE CAFE' | cafe' in the new science bldg | 2019-11-20 07:45 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 1377225 | 1165454 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | STARBUCKS RENOVATION | Renovate the Starbucks at Student Union | 2020-01-06 07:18 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 428309.49 | 345843.37 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 1007 | Union Deck | UNION DECK ELEVATOR | Replace elevator | 2020-06-15 14:38 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | NEILSON, JOHN (jneilson) | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 2108 | McColl-Richardson Field | Football Game Field Replacement |  | 2020-06-15 |  | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) |  | 20-0259-F |  | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 15100 | Academic Affairs VC | 0000 | Campus | STUDENT HEALTH & WELLNESS | UNC Charlotte currently has a significant shortage of student health and wellness activity space. A recent study by Brailsford and Dunleavy showed the campus has well under half of the facility space dedicated to student health and wellness by other | 2011-06-02 09:46 | RAJA, JAYARAMAN (jraja) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | NEILSON, JOHN (jneilson) | 66000000 | 63617441.1 | 0

## INFORMAL PROJECTS - ON HOLD
Project Priority List | [8 empty] | 2020-07-14 | [8 empty] | INFORMAL Projects - ON HOLD
Unit | Campus Priority | Control Code | Project Status Block | Project Type | Department Code | Sub Department Name | Bldg Code | Building Name | Project Request Name | Project Description | Date Created | Project Account Manager | Project Customer | Financial Account Manager | Scope & Budget Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed | Estimated Design Complete | Notes
AA | 6 | AA-1440 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0057 | Duke Centennial Hall | DUKE 349 RENOVATIONS | Convert faculty lounge to office spaceContact Kevin Scott Smith for details 7-8350 | 2017-09-07 12:39 | HUNTER, KATHY (kdwhaley) |  | HUNTER, KATHY (kdwhaley) | BOAL, JOHN (jboal1) | 18-0049 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 6-23-2020 : On hold.
AA | 6 | AA-1414 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD BIOLOGY CAMERA REPLACEMENT | Woodward Biology Camera Replacement | 2017-05-16 13:26 | HUNTER, KATHY (kdwhaley) |  | HUNTER, KATHY (kdwhaley) | CAUDLE, AMANDA (afelock) | 18-0010 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-7-20) Project on hold per Academic Affairs.
AA | 6 | AA-1638 | Project On Hold Design Services | Informal Projects | 15175 | Center City Campus | 0073 | Center City Building | CCB 1106 EXPANSION | Explore the possibility of remodeling and expanding 1106 at Center City. Remove wooden side walls and wall between 1106 and the storage areas behind it to make the room larger. | 2019-08-19 13:41 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | CAUDLE, AMANDA (afelock) | 20-0051 | CAUDLE, AMANDA (afelock) | 13000 | 0 | 0 |  | (7-7-20) Routed scope and budget for design 12/4/19. Pending customer approval to proceed. Placed on hold 6-26-20.
AA | 6 | AA-1673 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS 146, 149 CNT. FOR GRAD.LIFE MOVE FROM CONE | Atkins - 146, 148A, 148B, Suite 149 - Move Center for ¦Graduate Life from Cone 2nd floor to Atkins 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0125 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-7-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1698 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0080 | PORTAL | PORTAL 129 UPGRADES | Portal - 129 - Upgrades to Active Learning Classroom | 2020-03-16 08:25 | SCHAUBLE, DONIA (dcooke) | TANKERSLEY, RICHARD (rtankers) | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0199-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-7-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1692 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | BAND TOWER FOOTING DESIGN | Band Tower Footing Design - The marching band will be installing a pre-fabricated 24' tall steel tower at the practice field. The tower will need to have a footing designed by an NC licensed engineer. Getting a budget for this project is very urgent | 2020-02-12 10:38 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 20-0174 | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 |  | Restarting project, considering a temporary option + storage instead of the permanent tower. Arranging meeting with band group.
AA | 6 | AA-1610 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 391 RENOVATION | We are looking at splitting the room in two similar to 388/393.It may not be an exact half split though.We want one side to be a small PhD classroom and the other side to be a student bullpen area similar to 388/393.Classroom half needs to seat 20 if | 2019-04-10 13:24 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | TWEED, DANA (dtweed1) | HILL, CAROLINE (cmhill2) | 19-0204 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1616 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 242 CONFERENCE ROOM | I need a cost estimate to convert Friday 242 into a conference room. Move 1 display to the end wall. Remove the remaining 5 displays (Belk College Technology Team will take the 5 that get removed). Patch and paint walls. Core drill to connect lapto | 2019-04-22 13:35 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | SANCHEZ, STEPHANIE (ssanch12) | HILL, CAROLINE (cmhill2) | 19-0211 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1690 | Project On Hold Design Services | Informal Projects | 24200 | OneIT-CIO | 0001 | Kennedy | KENNEDY 320 RECONFIGURATION | We would like to discuss options for how Kennedy 320 can adjust for growth, specifically using 2 - 4 areas of existing space. Sandra Soriano (78987) is the contact for this request. | 2020-02-07 14:44 | VITALLO, JUDY (jvitallo) |  | VITALLO, JUDY (jvitallo) | HILL, CAROLINE (cmhill2) | 20-0170 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Scheduled to regroup on this project once campus has opened back up.
AA | 6 | AA-1540 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0037 | McMillan Greenhouse | GREENHOUSE FOR BIOLOGY FACULTY | Greenhouse for Biology Faculty | 2018-06-29 09:17 | HUNTER, KATHY (kdwhaley) | SCHAUBLE, DONIA (dcooke) | HUNTER, KATHY (kdwhaley) | PATEL, NAVINKUMAR (npatel24) | 19-0023 | PATEL, NAVINKUMAR (npatel24) | 228650 | 0 | 0 |  | (07.07.2020) Waiting on Donia for scope of work and to set up meeting with end user. ON HOLD
AA | 6 | AA-1668 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0058 | Grigg Hall | GRIGG 386 CLEAN ROOM MOVE FROM CAMERON | Grigg - 386A - Move portions of existing Cameron clean room to Grigg 386A . This will locate all campus clean room functions into Grigg.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:19 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0120 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Working with Wei Gao on scope for equipment moves Will engage designer once scope is detailed. Will follow up with Donia regarding design fee.
AA | 6 | AA-1676 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 217/218/220 SYST. ENGIN. MOVE FROM CAMERON | Smith - 205, 206, 211, 212, 213, 214, 216, 308,311,314,317,318,319,320, 320A,325,348,349,351,352 - relocate Systems Engineering from Cameron 2nd floor to Smith and create graduate bull pins for Engineering Technology graduate students who currently o | 2020-01-14 10:44 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0128 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Waiting on design fee from McVeign & Mangum. Will follow up with them this week.
AA | 6 | AA-1677 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 2 & 3 FLOOR CORRIDOR REFRESH | Smith - 245D and 2nd/3rd floor corridors - Provide AV upgrade for conference room 245D for use by Engineering Technology. Replace existing VCT possibly Asbestos containing in 2nd and 3rd floor corridors with LVT to match recently renovated hallways o | 2020-01-14 10:50 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0129 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | NNP - part of Cameron moves
AA | 6 | AA-1685 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS 330 NURSING SIMULATION LAB | CHHS - 330, 330A - Convert existing Classroom in School of Nursing Simulation Lab.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 11:12 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0134 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Waiting on Donia for equipment and project scope. ON HOLD
AA | 6 | AA-1702 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS VIRTUAL CADAVER LAB | CHHS - Virtual Cadaver Lab | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0205-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.07.2020) Waiting on information from Donia regarding location, and equipment. ON HOLD
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:10 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 |  | (6/30/20) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | 18000 | English | 0045 | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 2020-02-20 10:55 | WILLIAMS, ANGELA (anwillia) |  | WILLIAMS, ANGELA (anwillia) | SISCO, ASHLEY (asisco1) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (6/30/20) Per email from customer this project will be on hold.
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 2020-03-16 08:40 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (6/30/20) Per email from Donia on 5/27 this project will be placed on hold. Will revisit in 6 months.
AA | 6 | AA-1628 | Project On Hold Design Services | Informal Projects | 22000 | Mech Engineering & Engineering Sci | 0075 | Motorsports Research | MOTORSPORT WIND/TUN.STRUCT. ANALYSIS & POWER SPLY. | Motorsports Research Room 124 - Can we please have someone come out and approve the location of putting a concrete isolation pad in. Isolation pad will be provided by a 3rd party, we just need load approval for the floor below. | 2019-07-03 15:33 | CANTOR, MARION (mjcantor) |  | TADLOCK, ERICA (ewalter5) | SPATARO, EVAMARIE (espataro) | 20-0023 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Waiting on customer to assemble windtunnel and finalize where the equipment will reside in lab. Once complete, electrical can be run.
AA | 6 | AA-1632 | Project On Hold Design Services | Informal Projects | 17200 | Biological Sciences | 0056 | Woodward Hall | WOODWARD 461 EMERGENCY CIRCUIT | Woodward Hall - 461 - Add emergency circuit to lab (461). Almost a mirror project to the recently completed 361 | 2019-08-08 14:59 | GRAY, DAVID (dlgray) |  | GRAY, DAVID (dlgray) | SPATARO, EVAMARIE (espataro) | 20-0044 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Scope and budget provided to customer. Waiting on customer decision. Likely to be cancelled.
AA | 6 | AA-1645 | Project On Hold Design Services | Informal Projects | 22150 | EPIC | 1055 | Lot 6 | LOT 6 - EV CHARGING STATION | Lot 6 - EV Charging Station: Provide an estimate for design and construction cost to install an experimental EV charging location. | 2019-09-09 13:42 | BROWN, LORI (lmorri25) | GAFFORD, JAMES (jgafford) | MOOSE, ROBIN (rmoose2) | SPATARO, EVAMARIE (espataro) | 20-0059 | SPATARO, EVAMARIE (espataro) | 11000 | 0 | 0 |  | (7/7/2020) On hold.
AA | 6 | AA-1629 | Project On Hold Design Services | Informal Projects | 24400 | Research & Economic Dev. VC | 0080 | PORTAL | PORTAL INTERIOR GRAPHIC SIGNAGE | We want signage to raise the profile of the Office of Tech Transfer, SBTDC, Ventureprise, 49er Foundry, and the PORTAL Solutions Desk. Signage needs to large enough to be seen from across the lobby, attractive, and professional. All of these offices | 2019-07-15 14:23 | MATEEN, ALI (amateen) |  | KEENE, PATRICIA (pgkeene) | TERRY, STEPHEN (slterry) | 20-0032 | TERRY, STEPHEN (slterry) | 10800 | 0 | 0 |  | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1663 | Project On Hold Design Services | Informal Projects | 18050 | DPT Writing, Rhet, Digital Studies | 0042 | Cameron Hall | CAMERON WRITING PROGRAM 1ST FLOOR SIGNS | CAMERON WRITING PROGRAM 1ST & 2ND FLOOR SIGNS: Name changes needed to Department of Writing, Rhetoric and Digital Studies. Several signs throughout first and second floors need to reflect our new name. Please contact Denise Sabo 7-1902 | 2019-11-15 13:46 | SABO, DENISE (dsabo1) |  | MULLIN, JOAN (jmulli40) | TERRY, STEPHEN (slterry) | 20-0089 | TERRY, STEPHEN (slterry) | 2900 | 0 | 0 |  | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1706 | Project On Hold Design Services | Informal Projects | 15300 | College of Liberal Arts & Sciences | 0045 | Fretwell | FRETWELL 3RD FLOOR ATRIUM NAMING | Fretwell 3rd Floor Atrium Naming. Dr. Robert & Mrs. Tiwana Anderson Atrium Signage and Portrait development and installation | 2020-03-31 17:42 | FRIZZELL, MARY ELLEN (mfrizzel) | LEKOSKI-EURICH, JUDY (jlekoski) | STAFFORD, ELEANOR (eastaffo) | TERRY, STEPHEN (slterry) | 20-0217-I | TERRY, STEPHEN (slterry) | 5400 | 0 | 0 |  | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1669 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD 264, 275 KINESIOLOGY MOVE FROM CAMERON | Woodward - 264, 275, 276, 276AMove Kinesiology Research labs from Cameron 2nd floor to Woodward 2nd Floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:25 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0121 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (6/23/20) Project on temporary hold until customer is back on campus
AA | 6 | AA-1672 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0042 | Cameron Hall | CAMERON 174 MOSAIC MOVE FROM CAMERON | Cameron- Suite 174 - Relocate Mosaic from Cameron 2nd floor to Cameron 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:51 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0124 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (6/23/20) Customer meeting to schedule
AA | 6 | AA-1674 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0072 | EPIC Building | EPIC 1231 FURNITURE | EPIC - 1231 - Furniture Project - Exact scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble and Alicia Wells only. | 2020-01-14 10:01 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0126 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (6/23/20) Project on Hold
BA | 6 | BA-1631 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0068 | Bioinformatics | FPFM, BIOINFORMATICS 124 CODE ROOM USE SEPARATIONS | FPFM - BIOINFORMATICS 124 CODE REQUIRED ROOM USE SEPARATIONS: Mechanical, storage and wood shop uses need separation by 2-hour fire walls. Construction costs unknown. Outside design is required at $30,000. | 2017-11-02 06:48 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | BOAL, JOHN (jboal1) | 18-0089 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 6-23-2020: Project not funded.
BA | 6 | BA-1696 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1007 | Union Deck | UNION DECK STORAGE ROOM | UNION DECK Storage Room, provide large storage room on level 1 underneath of the up ramp where area is fenced off. This modification was rejected in the Expansion project due to schedule but we would like to review requirements and price out impleme | 2018-05-07 09:37 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | CAUDLE, AMANDA (afelock) | 18-0232 | CAUDLE, AMANDA (afelock) | 225000 | 0 | 0 |  | (7-7-20) Project on Hold
BA | 6 | UA-0039 | Project On Hold Design Services | Informal Projects | 30300 | Alumni Affairs | 0088 | Hauser Alumni Pavilion | HAUSER ALUMNI PAVILION SECURITY DOORS | Project to add garage door type security between the brick columns . Cleo - use 138062. Contact Scott Plunkett at 7-7792 | 2017-11-14 09:27 | PLUNKETT, SCOTT (ssplunke) |  | WIDMAIER, CLEO (cswidmai) | CAUDLE, AMANDA (afelock) | 18-0101 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-7-20) Project to remain on hold per Scott Plunkett.
BA | 6 | BA-1930 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0001 | Kennedy | KENNEDY CONTEMPLATIVE SPACE RENOVATION | KENNEDY CONTEMPLATIVE SPACE RENOVATION, DESIGN: Chancellor 2020 Central Funds: $50,000. Design Only. Project Dollar Maximum: $30,800.00. | 2020-03-04 07:20 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0184 | FRERE, ELIZABETH (efrere) | 30800 | 30800 | 30800 | 2020-04-15 | (05-08-2020) Watson Tate Savory total design contract reduced to $29,920. Partial invoice for $23,222.10 dated 04-23-2020 was approved for payment on 04-27-2020.
BA | 6 | BA-1586 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT: Congestion Task Force assignment for design only: Central Funds - Project Dollar Maximum: $13,000. | 2017-05-17 07:56 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | KELLY, SHAWN (skelly64) | 17-0225 | KELLY, SHAWN (skelly64) | 13000 | 13000 | 11731.7 | 2017-05-29 | On Hold till Funding Approved
BA | 6 | BA-1676 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, CAMPUS ADA PATHWAYS SURVEY DATA REVIEW | FPFM, REVIEW RECENTLY COMPILED CAMPUS ADA PATHWAYS SURVEY DATA TO MAKE RECOMMENDATIONS FOR CHANGES TO CAMPUS MAP: Point of contact: Katie Montie with Disability Services (DS). Facilities Information Systems (FIS) to provide technical assistance. | 2018-03-07 06:37 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 18-0178 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | Following Up with Customer To Closeout
BA | 6 | BA-1762 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1056 | Lot 7 | LOT 7 & 7A RECONFIGURATION | LOT 7 & 7A Reconfiguration, redesign Lots 7 and 7A to optimize usage and traffic flow (Design only at this point in time). | 2019-01-07 10:46 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 19-0106 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | On Hold Pending Cone Deck Decisions
BA | 6 | BA-1544 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS WIDE BUILDING EVACUATION MAPS | Building evacuation interior floor plan maps need to be installed in all buildings. The Office of Environmental Health and Safety would like to request an official scope and budget to install these maps. | 2017-03-07 16:43 | GRIFFIN, DARIUS (dgriffin) |  | GRIFFIN, DARIUS (dgriffin) | TERRY, STEPHEN (slterry) | 17-0195 | TERRY, STEPHEN (slterry) | 0 | 0 | 0 |  | (06-03-20) - Still on hold for funding. Scope was provided to EHS for funding review.
BA | 6 | BA-1680 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS SERVICE VEHICLE SIGNAGE | Please provide a proposed scope and budget for the project detailed below. Once the scope and budget is received, our office will be able to determine if the project can be completed this fiscal year or in the next.Approximately 15 marker post signs | 2018-04-02 16:44 | GRIFFIN, DARIUS (dgriffin) | ALSTON, TAMEKA (talsto16) | BARNETT, DENISE (dbarne33) | TERRY, STEPHEN (slterry) | 18-0198 | TERRY, STEPHEN (slterry) | 18500 | 0 | 0 |  | (06-03-20) - Still on hold for funding. Scope and preliminary designs were provided to EHS for review.
BA | 6 | BA-1871 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING: Need Scope & Budget to allow further review by Jon Varnell to allow assessment of funding options. Please assign to Steve Terry. | 2019-11-18 10:44 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | TERRY, STEPHEN (slterry) | 20-0088 | TERRY, STEPHEN (slterry) | 30000 | 30000 | 0 | 2020-06-12 | 06/03/20. No change. Budget review. Customer said to hold.
BA | 6 | BA-1959 | Project On Hold Design Services | Informal Projects | 10500 | Auxiliary Operations | 1057 | Lot 8 | LOT 8 HOUSING VEHICLES SIGNAGE | Install signs for Housing vehicles in Lot 8 (I would call "Lot 8 signage) | 2020-05-13 11:05 | HOLMES, ROBERT (rholme16) | LAPE, DOUGLAS (dlape) | MULLMANN, JANETTA (jmullman) | TERRY, STEPHEN (slterry) | 20-0240-I | TERRY, STEPHEN (slterry) | 0 | 0 | 0 |  | 06-03-20 - Site meeting on hold.
IF | 6 | SA-0444 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE NORTH ROOF REPLACEMENT | Cone North Roof Replacement - Fully remove existing system to replace the Cone North Building Roofing System. | 2019-12-09 13:04 | MERCK, DONNA (dlmerck) |  | HARRIS, MELODY (mhharris) | BOAL, JOHN (jboal1) | 20-0112 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 6-23-2020: Project on hold.
IF | 6 | BA-1854 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0046 | Barnhardt Student Activity Center | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION: Investigate smoke management of SAC during fire alarm activation. AHU devices do not shut down; smoke purge system serving the food court does not function. Assign to Don Janus. | 2019-07-23 08:33 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 20-0034 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | 06/27/20: On Hold Pending Review with Engineering Dept
IF | 6 | BA-1913 | Project On Hold FAM | Informal Projects | 13115 | Safety and Security | 0000 | Campus | CAMPUS SIREN UPGRADE "ALERTUS" | Safety & Security - Campus Siren upgrade - "Alertus" | 2020-01-31 11:09 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | LOVE, DAVID (dflove) | 20-0162 | LOVE, DAVID (dflove) | 0 | 0 | 0
IF | 6 | BA-1944 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | STARBUCKS TRUCK PAD AND ELECTRICAL | STARBUCKS TRUCK Pad and Electrical, provide design to provide a prototypical pad off off the sidewalk for Starbucks Truck to pull over and sell during the day. Initial location is intended to be Smith but pad could be used anywhere - need pull off, | 2020-04-10 12:56 | AVERITT, DREW (daveritt) | THOMPSON, JODY (jthom373) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0221-I | SMITH, RYAN (rsmit341) | 26000 | 0 | 0 |  | Project on Hold per DA per 6/16/2020 Email
IF | 6 | AA-1655 | Project On Hold Design Services | Informal Projects | 15175 | Center City Campus | 0073 | Center City Building | CCB OUTDOOR LIGHTING | Additional lighting needs to be added to the back garden area. Please assess the current lighting, make recommendations for additional and adequate lighting and provide an estimate of cost. | 2019-10-10 12:30 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | SPATARO, EVAMARIE (espataro) | 20-0079 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Customer has received estimates. Waiting on decision.
IF | 6 | BA-1889 | Project On Hold Design Services | Informal Projects | 13115 | Safety and Security | 0046 | Barnhardt Student Activity Center | FIRST PRIORITY CAMERA PROJECT PHASE 2 | Please assign to David Love - Phase 2 includes SAC, West Deck, Belk Gym, Cone, Colvard, Levine Hall, Cato, Prospector, McEniry, Auxiliary Services, Cameron, Bioinformatics, PORTAL, EPIC, Grigg, Duke, Motorsports, South Village Deck. (Approximately 2 | 2020-01-07 10:31 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | SPATARO, EVAMARIE (espataro) | 20-0115 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Defining Scope & Timeline with Customer. On hold until priority 1 is complete.
SA | 6 | SA-0408 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE SOUTH 3 MODERNIZATION | Cone Center - South 3: Upgrade and modernize South 3 level of Cone Center. Collaborate with Director and Associate Director to establish design options and features. | 2019-01-31 13:53 | MERCK, DONNA (dlmerck) |  | MERCK, DONNA (dlmerck) | CAUDLE, AMANDA (afelock) | 19-0147 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-7-20) On hold - waiting for Morgan and Donna to provide scope of work
SA | 6 | SA-0450 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION M101 ESPORTS LOUNGE | There is a space identified in the Student Union as a potential opportunity for an Esports Lounge. Need to determine if it is feasible in the space given the needs of the group. Need feasibility information by 1/28 and then will proceed further if ne | 2020-01-16 10:59 | MEEHAN, MORGAN (mmeeha11) |  | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 20-0137 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (7-7-20) Informal budget provided to Morgan Meehan 1-27-20. Pending approval to proceed. Placed on Hold April 27.
SA | 6 | SA-0462 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS AND PREFUNCTION CARPET | Project is to gather estimates and designs on replacing the carpet inside and outside of the SAC Salons. | 2020-03-16 08:40 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | HILL, CAROLINE (cmhill2) | 20-0202-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/29/2020 - Customer would like to wait until we return to campus to proceed with project.
SA | 6 | SA-0407 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0077 | Halton-Wagner Tennis Complex | HALTON TENNIS COMPLEX LOWER HALL FLOODING | The lower hallways of the Halton Tennis Complex flood when there is heavy rain. Zone 1 has performed some modifications to the weep holes in the brick which has helped but we are still getting some flooding. The water drains towards the building inst | 2019-01-24 16:57 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 19-0134 | LANIER, LISA (llanier) | 34000 | 0 | 0 |  | 02-13-2020 Discussed project with Cass Ferguson. Project does not have funding at this time. Needs further discussion due to continued water infiltration. Does not appear to be site related.
SA | 6 | SA-0439 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 062 FITNESS ROOM RENOVATION | Fitness room renovation two include two spaces; one space is to remain a multipurpose room for events and the other space is to be converted into offices and storage space. Would like to keep as much of original hardwood floor as possible. | 2019-10-09 09:37 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | LINGER, JOSHUA (jlinger2) | 20-0070 | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 |  | 07/07/2020 -Project on hold while Customer determines if they have other options.
SA | 6 | SA-0441 | Project On Hold Design Services | Informal Projects | 28900 | University Recreation | 0017 | Belk Gymnasium | BELK GYM 127 RECONFIGURE | Adding a door and wall to create a designated space to be used after UREC moves from Belk Gym to UREC building. Separating COR10 from 127 | 2019-10-16 13:31 | BELL, ROBERT (rbell16) |  | BARRETT, LACRISSA (lbarre11) | LINGER, JOSHUA (jlinger2) | 20-0074 | LINGER, JOSHUA (jlinger2) | 9987.5 | 0 | 0 |  | 07/07/2020 -Project on Hold per email from Robbie Bell 02/24/20. Overall price ($9,988) was more then they expected. They will use the space as is for now to determine necessity of project.
SA | 6 | SA-0388 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC ARENA BB & CURTAIN - LOW VOLTAGE | Change existing retractable basketball goals and mechanical partition curtain systems in Halton arena from 120v to low voltage. | 2018-07-26 14:21 | MOON, STUART (sgmoon) |  | BARNES, TRENT (tbarne21) | SPATARO, EVAMARIE (espataro) | 19-0038 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) On hold.
SA | 6 | SA-0424 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION LED LIGHTING RETROFIT | Student Union - Entire BuildingStudent Union wants to increase sustainability by reducing energy consumption and decrease annual maintenance cost for replacement fluorescent lights by retrofitting lighting to LED. This project aligns with UNC policy | 2019-06-24 09:37 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | SPATARO, EVAMARIE (espataro) | 20-0022 | SPATARO, EVAMARIE (espataro) | 43000 | 0 | 0 |  | (7/7/2020) On hold.
SA | 6 | SA-0440 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 334A-E SALONS LIGHTING UPDATE | Replace light fixtures, and update control system to accommodate new lighting. | 2019-10-09 09:42 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | SPATARO, EVAMARIE (espataro) | 20-0071 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (6/30/2020) Project can be FF&E. Will work with customer to schedule. Customer holding for funding.
SA | 6 | SA-0455 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 340 POWER UPGRADE | Student Union would like to add additional power to the multi purpose room 340. We are looking at 100A, 3 phase, 5 wire, 120/208V. Requesting Eva Spataro on this project | 2020-02-18 16:03 | BROWN, JOSHUA (jbrow450) |  | MEEHAN, MORGAN (mmeeha11) | SPATARO, EVAMARIE (espataro) | 20-0186 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | (7/7/2020) Sent scope and budget to customer. Customer taking S&B to lobby for funding.
SA | 6 | SA-0442 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0017 | Belk Gymnasium | BELK GYM 120 VENTURE MOVE | Venture has been approved to move from Cone to Belk gym. Within this project includes: coordinating a move of the staff, office furnishing needs, space renovations in Belk for storage space. As this project is related to project SA-0441 it could be | 2019-10-24 14:09 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | WELLS, ALICIA (awells43) | 20-0080 | WELLS, ALICIA (awells43) | 160000 | 160000 | 0 | 2020-07-31 | (6/23/20) Project ready for order placement but on hold until FY21

## FORMAL PROJECTS
Project Priority List | [8 empty] | 2020-07-14 | [8 empty] | FORMAL Projects
Unit | Campus Priority | SCO Project ID | Project Status Block | Project Type | Department Code | Sub Department Name | Bldg Code | Building Name | Project Request Name | Project Description | Date Created | Project Account Manager | Project Customer | Financial Account Manager | Scope & Budget Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed | Estimated Design Complete | Notes
| 0 | 19463 | Created | Capital Projects | 13900 | Facilities Management AVC | 0020 | McEniry | MCENIRY HVAC PHASE 4 | Replace HVAC in McEniry | 2019-11-19 15:06 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | BOAL, JOHN (jboal1) | 7336875 | 9521643 | 0 |  | Consultants Jenkins Peer Architects - designer McCracken and Lopez - mechanical engineer New Atlantic - CM@R Milestone dates and activities PGMP Contract sent to SCO 6/3/2020 for Notice to Award. Armstrong Mechanical started work 6.12.2020 on the summer package and is on schedule to complete in August. Summer package was bid separately and is not part of the CM@R scope. Subcontractor pre-qualification for the larger project has been completed by New Atlantic and submitted to UNC Charlotte. Work in Labs will be funded by AA and completed by another contract. Includes demo, abatement, new duct work and VAV for future labs. Redesign of the labs to reduce the scope of work had begun and will be completed in the third week of July. PGMP Contract sent to SCO 6/3/2020 for Notice to Award. Summer work began 6.26.2020. AHU-2 work scheduled completion 7.10.2020. Begin AHU-3 duct demolition 7.13.2020.
| 0 | 21522 | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | STARBUCKS RENOVATION | Renovate the Starbucks at Student Union | 2020-01-06 07:18 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 428309.49 | 345843.37 | 0 |  | Consultants Biloba Architecture MV Momentum LLC Milestone dates and activities Received Starbuck preliminary design in December 2019. Received SCO approval to bid March 4, 2020. Corrected CD documents to be resubmitted March 16, 2020. Starbucks provided FF&E contract signed by Drew Averitt April 17, 2020. Request for pricing sent to (3) contractors - Heartland, I.L. Long, Momentum - April 20, 2020 with pricing due by 3pm on Wednesday, April 29, 2020. Momentum Construction low bidder at $250,596 including alternate 2 owner preferred flooring. Construction started Monday, May 18, 2020 - to complete Tuesday, August 4 Weekly construction progress meetings on Monday’s at 9am. Front of house ceiling changed from hard ceiling to drop ceiling per Starbucks approval June 23, 2020 - this should help with cost and schedule. Issues to be resolved Better schedule - Momentum presented a revised scheduled on June 15 that showed completion on August 14 with another 2 weeks for Starbucks install. Turnover of the store must be no later than August 14 to allow for 2 weeks of stocking and training before opening.
| 0 | 21438 | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | POPP MARTIN STUDENT UNION | renovate Einsteins, New Venue & Crown Commons | 2019-11-20 05:53 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 9638114.5 | 9111644 | 0 |  | Consultants Moseley Architects - designer Shiel Sexton - CM@R McCracken & Lopez - commissioning agent Milestone dates and activities Kick off meeting held Tuesday, March 24. Conceptual plan review meeting scheduled for Thursday, May 28. Workshop #2 held Wednesday, June 10 from 1-3pm. Moseley/Tipton site visit June 23 & 24. Moseley/Tipton schematic design review meeting scheduled for July 9. Construction planned for May 2021 - August 2021.
| 0 | 19041 | Created | Capital Projects | 15100 | Academic Affairs VC | 0068 | Bioinformatics | BIOINFORMATICS 4TH FLOOR UPFIT | Build-out 4th floor to provide interdisciplinary research space to support UNC Charlotte's need for labs and faculty offices. | 2018-06-04 10:33 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 10500000 | 9367077.83 | 0 |  | Consultants Designer - LS3P Lab Planner - RFD CM@R - Balfour Beatty Milestone dates and activities Balfour Beatty selected as CMR, precon contract approved by SCO and sent to Balfour for signature April 30, 2020 Alternates discussed March 16, 2020 CMR submitted SD/DD phase cost estimate on April 8, 2020 SD/DD reconciled cost estimate reviewed on April 16, 2020, within budget and approved to move forward without any revisions Design contract routed for University signatures on April 13, 2020 Project taken off hold, restarted design process after Design contract was executed on 6/11/20. CD Kickoff Meeting scheduled for July 20, 2020 SCO approved SD/DD phase submittal on May 21, 2020 Issues to be addressed BSL3 valve funding issue still on-going - design and construction to be an informal project, trying to locate funding for total project total +/-$400,000
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | CAMPUS STORM WATER PROJECT - PHASE II | Authorization is $850,000 - Capital budget is $750,000. Storm Water Volume Control r-58. #2 priority project in Storm Water Master plan. Required to bring us into compliance with Clean Water Act.The restoration of Toby Creek is proposed as a partners | 2013-12-16 16:34 | FESSLER, JOHN (jafessle) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 750000 | 342859.45 | 0 |  | Campus Regional Stormwater Master Plan Elizabeth Frere Consultants Surface 678 Milestone dates and activities Master Plan Production Schedule Stormwater overview presented at BOT February 11, 2020 Outline of final to be submitted to UNC Charlotte for review on June 12, 2020 Draft of final report to be submitted to UNC Charlotte for review and comments on June 19, 2020 Final draft completion date has been extended because the draft can’t be complete until: additional analysis of the garden area is finished and we receive responses from the City on the last round of questions. University is currently reviewing in Bluebeam University (assisted by Surface 678) submitted PCSO letter & timeline to the City on October 17, 2019. Resubmitting existing SCMs that are currently receiving partial or no stormwater credits to the City Surface is analyzing existing SCMs on campus that were never submitted to the City (UREC, FOPS) or receiving partial credit (EPIC, Lot 27, Phase XII, Phase XIII, South Village Deck) Additional cost proposal from Surface (consultant is Wildlands) to be submitted as soon as they collect all the needed documentation for the above SCMs - anticipated cost +/- $60,000. Issues to be addressed Cost for potential first phase identified for inclusion in the FY21-25 Capital Plan Clarification of FM team roles and responsibilities - Elizabeth is PM, Greg is working closely with the project team. Final revisions & clarifications to MOU under way.
| 0 | 11004 | Created | Capital Projects | 13900 | Facilities Management AVC | 0000 | Campus | CRI ENTRANCE ROAD | Create a new entrance off Hwy 29 | 2019-11-20 05:15 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 1449300 | 1159589.44 | 0 |  | Consultants TBD Milestone dates and activities Designers were interviewed April 1. Approval of designer - sent to Jon Varnell Has the designer submitted a fee proposal? No, the designer has not been approved - cannot make contact to request a proposal. CDs complete in August 2020 assuming design begins in a timely manner. Construction January 2021 - April 2021. Issues to be addressed CDoT approval for proposed entrance design from North Tryon Need to block entrance to TCE when Choate has completed their work to prevent unauthorized access.
| 0 | 21436 | Created | Capital Projects | 13900 | Facilities Management AVC | 1054 | Lot 5A | LOT 5A | re-alignment of lot 5A | 2019-11-19 14:10 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 702248.85 | 742025 | 0 |  | Consultants Dewberry - designer Milestone dates and activities submitted to SCO on 5/22. SCO Construction Approval received 6/2. Owner comments received 6/5. FMEng review of comments with Dewberry on 6/29 Bid advertisement to follow - by 7/2. Selecting a Construction Services firm from the Open Ended list. Construction anticipated to begin July 2020. Issues to be addressed Preliminary cost estimate for selected concept: $241,000 for the initial design. As of 4/20: $6,000 savings from lighting estimate $50,000 add for trees and internal islands $165,000 add for stormwater cost sharing $450,000 total construction cost Revision to the added impervious area due to Lot 5A has changed the amount for stormwater management to $107k. Tree islands will be bid as an alternate, as will the relocated bus stop and associated pull off and sidewalk. The project is over budget by $17k Trees being planted in islands for $50k were not part of initial project scope. Dewberry has added an alternate to include 6 trees internal to the parking lot which carries an estimate of $50,000. PaTS budget is $450,000. Initial Capital construction cost estimate was $449K. This includes the Lot 5A Expansion share of the stormwater management being constructed by the East Village Infrastructure project. Based on updated stormwater pricing, EVI is covering ~$107k in Lot 5A costs.
| 0 | 21434 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | RECLAIMED WATER | The University has developed a proposed partnership with Charlotte Water (City of Charlotte) to bring reclaimed water to campus from the Mallard Creek waste water plant. This water will replace potable water currently used in chillers and boilers on | 2016-12-15 07:53 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 2100000 | 1965355.27 | 0 |  | Consultants AECOM - Designer Milestone dates and activities Recurring bi-weekly web meetings with the Design team to continue through CD completion Schedule for the University project will be dictated by the Charlotte Water project. Have requested their updated schedule several times. Charlotte Water bids received for the off-campus portion of the reuse line on Thursday, April 2. Design estimate of ~$5M vs low bid of $3M. Charlotte Water rejecting all bids and re-advertising. Anticipating construction completion of full Reuse line in late-2021. On-campus construction anticipated to start construction in July 2020. Reveiwed the Communications Plan (Developed by PDF, FMEng, FMComms, UComm) with KH, JV on 6/19. Received approval on the plan with the request to involve Mike Lizotte moving forward. Issues to be resolved Costs associated with sampling, testing, and monitoring equipment and fields when reclaimed water is introduced as a source for cooling tower water and irrigation is being evaluated by Facilities Engineering. Return on investment analysis must be updated Project budget is $2.1M for design and construction. Monitoring data points and integration into University dashboard Scheduling charettes with FO and Grounds once a design amendment can be issued. Design team w/FO, ENGR planned to visit Chapel Hill to review their reclaimed water system on March 16, 2020. Trip postponed due to travel restrictions. Action Items (in development with Greg Cole, Richard LaLiberte) Negotiate additional services for surveying, water polishing design, monitoring design and integration, irrigation and mechanical charrettes. (Brian) Draft Design Amendment to be received by June 5. Forwarded to Shawn Kelly on 6/19 to start approval process so that the formal request for amendment can be sent to SCO. Schedule charrettes (Brian) After execution of Design Amendment Schedule update (Brian) include design charrettes and other new scope items included. include off campus items too. Contingent upon Design Amendment execution and receipt of schedule update from Charlotte Water Get alignment by alignment updated cost estimates and projected demands and develop cost/payback analysis for each (Greg) AECOM to provide opinion of construction cost for each alignment. Received 6/29 Date (1 week after AECOM provides the numbers) Update financial analysis for the project using what-if bid day scenarios. (Greg) Will generate three scenarios using reasonable assumptions. Will be able to plug in AECOM's estimates when they are available. Task complete by end of June. Send preliminary revised horizontal alignments for review and comment by FM. Meeting set for June 9. Received approval from FM leadership on new alignments. Complete communication plan and forward for review by Kathryn/Jon/others Complete by June 12 (Greg/Brian/FM Comms) Presented to Kathryn/Jon on June 19. Revise Reclaimed Water Agreement with Charlotte Water (Brian, as needed) The SS easement is our leverage to renegotiate the agreement. We don't know yet if we will need to renegotiate the agreement. Situations where we may want to renegotiate: We are not able to complete the project on time and need to delay repayment till our system is ready for use. We are not able to use the full amount of allotted reclaimed water because we are not able to build all 4 alignments. Council of State project Easement approval (for RCW Line & Sewerline): July 7th 2020 Obtain RCW Agreement Contract #: : upon execution (with final/revised terms), Ask City to "log-in" the agreement and assign a contract # within its contract (dbase) system. Contract # will be used for future reference and will mark the FINAL document terms. Appraisal information: Requested (from Andrew Ponder) for my file on 25Mar2020 (awaiting)--(PM City Real Estate/A. Ponder). I requested a status update 6/4/2020 Add reference "Layer": Add/overlay the Toby Creek RESTORATION project/easement lines (Brian/Fred: FIS/GIS) on the working RCW drawings. This is UNCC internal mapping vs consolidation on the formal RCW easements Greg mentioned: Sh 5 of 14 "...shows a gap between the existing SS and the new SSE" (Brian/Santec)
| 0 | 17048 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | East Village Infrastructure | East Village infrastructure including Martin Village Road re-alignment, Van Landingham bridge, lighting, telelcom, storm, sanitary and the electrical extension to the campus substation. Includes a traffic signal at John Kirk Drive. | 2013-10-08 08:26 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 4135056.7 | 7306234.75 | 0 |  | Consultants Kimley Horn - designer Shiel Sexton - CM at Risk Milestone dates and activities Third City/SCO CD submitted in December City comments received the week of Feb 10. SCO review comments received on March 2. Request for Increase in Authorization submitted at April BOT and BOG meetings to add funding from NCDOT and CDOT. 100% CDs to SCO as soon as July 30, 2020 Issues to be addressed Some scope from EVI will be bid in both EVI and Lot 5A Expansion as the projects work to share costs for the stormwater EVI is installing for 5A. Removing the $107,000 in cost sharing scope will allow for acceptance of removed alternates. Identified three scopes for bidding in both Lot 5A Expansion and EVI: Moving entrance to Lot 5 to line up with the designed Martin Village Connector (est $75,000) Installing the temporary sediment trap that will be converted to the Lot 5A Sand Filter at the completion of EVI construction (est $80,000) Constructing the wood safety rail around the Lot 5A Sand Filter. (est. $60,000) Conference calls on 3/18 and 3/25 with CDOT discussed removing Martin Village Connector from Base project scope. Received approval to proceed with the redesign and associated traffic modeling CDOT issued formal approval that the Martin Village Connector could be bid as an alternate, contingent upon a letter from the University that if the alternate is not taken, the scope would be added for completion on the University’s capital plan. Need to respond to CDOT on whether the University is amenable to this requirement. Shiel Sexton PGMP Proposal sent to Shawn Kelly on June 18 to begin the approval process so that the Award Request can be sent to SCO. Working through details of revising the Martin Hall BMP wall to avoid power/telecom ductbank with FM Engineering. Issue was presented by Kimley Horn and SS on 5/21 Kimley Horn working on a potential solution to be evaluated by PDC and Eng prior to incorporation in the 100% CDs. Kimley Horn has moved retaining wall back from duct bank and will lower the bottom of the pond to make up capacity. Concept approved for development by Cole, Kugler on 6/3. Advertisement for SI/CMT services posted on 6/12. Submittals due 7/8. Owner review set for 100% CDs distributed on 6/10. Comments requested by CoB on 6/15. FM Engineering requested extension through 6/18. Reviewed comments with FMEng and designers on 6/29. Comments to be addressed by the end of July for final submittal to SCO.
| 0 | 11494 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | EAST VILLAGE UTILITIES | The project is for the construction of utility infrastructure to support improvements to the East Village sector of campus to include water, telecom, and high voltage electrical service. | 2015-03-12 09:37 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 2100000 | 1279159.45 | 0
| 0 | 21440 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | WEST SUBSTATION | Project adds a second electrical substation to feed electricity from Duke Energy 100 KVA supply on the west side of campus (across W.T. Harris). This is needed to provide redundancy to our electrical source to insure fail safe operation for research | 2013-10-08 10:19 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 6500000 | 2539400.2 | 0 |  | Schedule to complete testing of 45 remaining cable lengths would be three weeks. Remaining contingency is enough to cover the cost of replacing longest length of cable on campus Engineering has met with FO to discuss this project. Majority of testing can be done without interruption of power to buildings (looped system). Circuit K, Seg 1: Outages would occur in Martin, Hawthorne, SHC, Counseling Center, FM/PPS and Annexes Circuit D, Seg 11: Levine Hall and HRL Circuit D, Seg 7: East Decks, Lots 4, 4A, Lot 6, Cato, Storrs, Band Center Circuit K, Seg 2: Martin Hall McKim & Creed Design Amendment #2 reduction of scope and fees routed for University signature to send to SCO.
| 0 | 14355 | Created | Capital Projects | 13900 | Facilities Management AVC | 0097 | Science Building | SCIENCE CAFE' | cafe' in the new science bldg | 2019-11-20 07:45 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 1377225 | 1165454 | 0 |  | Consultants BUILT - Chartwells Consultants for SD Clark Nexsen - Designer for DD, CD, CA Milestone Dates and Activities Meeting held April 1st with Chartwells and Built for scope clarification. BUILT SD proposal and contract executed 05/05/2020; Design fee: $3,780.00. BUILT working with Auntie Anne’s for preliminary plan layout. Plan revisions reviewed June 11th with Chartwells and Auxiliary Services. Clark Nexsen fee proposal revisions received; contract routed for execution. Construction cost budget is $850,000. SD design complete. SD/DD handoff meeting to be held with Built and Clark Nexsen on July 22nd. CD’s to be complete December 2020. Bidding to occur January 2021. Construction to begin April 2021 after completion of Science Building construction.
| 0 | 14054 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | SCIENCE BUILDING | The Science Building will provide important undergraduate class laboratory and interdisciplinary research space for UNC Charlotte. Many of UNC Charlottes buildings were constructed before doctoral instruction and, in some cases, before master leveli | 2011-06-02 09:30 | RAJA, JAYARAMAN (jraja) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 90000000 | 96854877.13 | 0 |  | Clark Nexsen - Designer Balfour Beatty - CM @ Risk Jenkins Peer - Feature Wall Design Consultant Milestone Dates and Activities: RUP/Data Center Commissioning nearing completion; Final BO date pending Cx Agent completion letter. Science building curtain wall South and East installation ongoing. Masonry installation ongoing, with areas D & E East complete, Areas B & C North ongoing. Gutter system complete. Duct Bank connections East side complete. MEP overhead rough-ins Levels 1-3 ongoing. Science schedule is showing improvement with roof dry-in, now tracking 7 days behind with billings below the curved value. Feature wall design underway with kick-off brainstorming session held May 27th. Final deliverable proposed review date 07/30/2020. Issues to be resolved: Cx comments have had improved response from the Design team and Balfour Beatty, and will continue to be assisted by weekly Cx meetings outside of the OAC. First weekly Cx held 04/30. Weekly Cx meetings continue and are beneficial in conveying Cx Agent’s expectations for inspections and completion. Progress with log deficiencies is noted. Cx requirements for BO need to be defined for Science Building with mindfulness to schedule; meeting to be scheduled to discuss and agree to expectations. Owner Reserve Requests continue to be tightly monitored and controlled.
| 0 | 22031 | Created | Capital Projects | 13900 | Facilities Management AVC | 1007 | Union Deck | UNION DECK ELEVATOR | Replace elevator | 2020-06-15 14:38 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | NEILSON, JOHN (jneilson) | 0 | 0 | 0 |  | Meeting with PaTS occurred on 06/18/20 to discuss budget and scope. Design RFP posted to university website and GA on 6/18/20 Proposals due 7/10/20.
| 0 | 12165 | Created | Capital Projects | 15100 | Academic Affairs VC | 0000 | Campus | STUDENT HEALTH & WELLNESS | UNC Charlotte currently has a significant shortage of student health and wellness activity space. A recent study by Brailsford and Dunleavy showed the campus has well under half of the facility space dedicated to student health and wellness by other | 2011-06-02 09:46 | RAJA, JAYARAMAN (jraja) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | NEILSON, JOHN (jneilson) | 66000000 | 63617441.1 | 0
| 0 | 21437 | Created | Capital Projects | 13900 | Facilities Management AVC | 0045 | Fretwell | FRETWELL CAFE' RENOVATION | Renovate Fretwell Cafe' | 2019-11-20 05:38 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | SISCO, ASHLEY (asisco1) | 722500 | 722500 | 0 |  | Consultants Watson Tate Savory - designer Milestone dates and activities Kickoff meeting held June 16. Reviewed high level floor plans and received agreement on one to develop. Met with WTS and Optima for field verification week of June 22. Design review meeting schedule July 14.
| 0 | 19671 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | INFORMATION TECHNOLOGY INFRASTRUCTURE UPGRADES | IT Infrastructure Upgrades in Rowe, Storrs and Reese | 2018-10-18 11:02 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 3800050.24 | 3140199.43 | 0 |  | Consultants Optima Engineering - Designer Shiel Sexton - Shiel Sexton CM@R Milestone dates and activities Project revised to reduce scope and put in as add alternates Construction anticipated to begin in Storrs in June 2020. Anticipated completion of construction, 168 days from NTP (date?). Pre bid conference 4.14.2020 PGMP request sent to SCO April 27, 2020 for Notice to Award University signed PGMP contract.5.25.2020, however, SCO wouldn’t accept electronic copy. 4 original copies will be forwarded to Beth for signature. Bid opening delayed until June 23rd. Sending contracts to SCO 6.9.2020 Contracts sent to SCO 6.12.2020 Issues Bid cabling as an alternate Bids received 6.24.2020, appears all alternates except rollup door and windows will be accepted. Shiel Sexton submitted final contract information to SCO 7.7.2020. Precon to be set up as soon as SCO approves contract.
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0000 | Campus | FO - FACILITIES OPERATIONS COMPLEX | The current Facilities Operations building is located on the proposed site of the new Science building. A new Facilities Operations building (32,000 square feet) must be constructed in order for the existing facility to be demolished. A new Receiving | 2011-06-02 15:57 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 24298000 | 22845568.77 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 2108 | McColl-Richardson Field | Football Game Field Replacement |  | 2020-06-15 |  | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) |  | 20-0259-F |  | 0 | 0 | 0
| 0 | 21759 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0069 | Popp Martin Student Union | STUDENT UNION - CROWN COMMONS RENOVATION | The Student Union was completed in 2009. The 9300 SF "Crown Commons" Dining Facility is a highly trafficked area utilized by thousand of patron daily. By the time this project occurs, the facility will be 10 years old and will need renovations includ | 2016-12-14 11:25 |  |  | PAQUETTE, NOELLA (njpaquet) |  |  |  | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | McEniry Chiller Replacement |  | 2020-06-11 |  | JANUS III, DONALD (drjanus) | WITHERSPOON, MELANIE (mewither) |  | 20-0264-F |  | 0 | 0 | 0